## Status
STD Appendix # | TSW Test case | Sub case | section | Title | Scripts Executed | CC Version of Script Executed | planned Run Date | Test Operator | Witness | actual run date | SIRN Run On | Script Run ID | Run Status P/F | Estimated duration (minutes) | proc edits made | ready for dry run | Comments / related DR's with status | Re-run Status | Re-run Operator | Re-run Date | Estimated Hours to Completion for Review | Task Status Redlines Script Update Procedure Update Action DR Review | Notes | LM/Aero Reviewer | Accept/ Reject | Comment
If tester does not understand these, read Use Case (VOB Systems in Clear Case ) and confirm requirements are covered in the Test Case. Verify GUI Screen Shot on STD matches GUI current SIRN display.
7.1 | 1 | 1 | 1 | Initial Setup | None | [8 empty] | 5 | [8 empty] | Known Issue - Add to reference document
|  |  | 2 | Confirm TSW (desktop shortcuts) | None | [8 empty] | 20
|  |  | 3 | Confirm SQL Sever Management Studio is avaliable on the PC. | None | [8 empty] | 1
|  |  | 4 | Power on and configuration verification. | None | [8 empty] | 1
|  |  | 5 | Record SIRN ID for the TSW being used for TSW SIQT. | Utility_MDU_Software_Version.xts | [8 empty] | 25
|  |  | 6 | Configure MDU and STE to a "Nominal" operational state. | Utility_MDU_Power_OnOff.xts (OFF) | [8 empty] | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [8 empty] | 5
[5 empty] | MDU_Configuration.xts | [8 empty] | 40
|  |  | 7 | Optional: Used during testing to do a Soft Reset to the MDU. | Utility_MDU_ReInitialization.xts |  |  | OPTIONAL |  | OPTIONAL |  |  |  | 15
|  |  | 8 | Optional: Use for Restoring STE to a Nominal Test Execution Working State | Utility_MDU_Power_OnOff.xts (OFF) |  |  | OPTIONAL |  | OPTIONAL |  |  |  | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | OPTIONAL |  | OPTIONAL |  |  |  | 5
|  |  | 9 | Calibration Factors Storage and Retrieval Test | TSW_SIQT_Create_and_Store_Calibration_Data.xts | [8 empty] | 5
[5 empty] | TSW_SIQT_Create_and_Store_Calibration_Data.xts | [8 empty] | 5
[5 empty] | TSW_SIQT_Create_and_Store_Calibration_Data.xts | [8 empty] | 5
[5 empty] | TSW_SIQT_Create_and_Store_Calibration_Data.xts | [8 empty] | 5
[5 empty] | TSW_SIQT_Create_and_Store_Calibration_Data.xts | [8 empty] | 5
7.1 | 2 | 1 | 1 | Nominal State | None | [7 empty] | - | 30 |  |  | Cannot complete – Do not have admin rights to change system time
|  |  | 2 | Establish AR PC Control | TSW_SIQT_Bad_Syntax.xts | [7 empty] | F | 15 |  |  | MA 2/16, 68, no STATE_ERROR
|  |  | 3 | Prompt Operator from AR STE | TSW_SIQT_Prompt_Operator_MAR.xts | [7 empty] | F | 5 |  |  | MA 2/16, 103, info script engine
[5 empty] | TSW_SIQT_TlmSerial_fail.xts | [7 empty] | - | 40
|  |  | 4 | Restore ITE Control | None | [7 empty] | P | 5 |  |  | MA 2/16
|  |  | 5 | Prompt Operator from ITE STE | TSW_SIQT_Prompt_Operator.xts | [7 empty] | P | 5 |  |  | WG 2/22, updt run with QA
|  |  | 6 | Detection of Faults at Startup | None | [7 empty] | P | 20 |  |  | MA 2/17, WG updt run
|  |  | 7 | Detection of disconnected cable from STE | None | [7 empty] | - | 15
|  |  | 8 | Disconnected AR Ethernet cable | None | [7 empty] | P | 15
|  |  | 9 | AR Instrument Power Down detected by ITE | TSW_SIQT_Self_Test.xts | [7 empty] | P | 10 |  |  | WG 2/14
|  |  | 10 | Process Startup-Shutdown | AAAA_MDU_Set_Config_Var_Utility.xts | [7 empty] | P | 5 |  |  | MA 2/18
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts | [7 empty] | P | 5
[5 empty] | TSW_SIQT_OS_Services_NotLoaded_TLM_Test.xts | [7 empty] | P | 10
|  |  | 11 | Invalid Startup Configurations | None | [7 empty] | P | 25 |  |  | MA 2/18
|  |  | 12 | Detect Invalid Configuration With Missing Configuration File | None | [7 empty] | P | 15 |  |  | MA 2/18, Proc updated
| 2 | 2 | 1 | Test Software configuration files | TSW_SIQT_Prompt_Operator.xts | [7 empty] | P | 5 |  |  | MA 2/18
|  |  | 2 | ITE Primary Controller of AR | TSW_SIQT_Calibration_MAR.xts | [7 empty] | P | 15 |  |  | MA 2/18
|  |  | 3 | AR Test Configuration Data | None | [7 empty] | P | 20 |  |  | MA 2/18
|  |  | 4 | AR Calibration Expiration Test | None | [7 empty] | P | 28 |  |  | MA 2/18
|  |  | 5 | ITE Calibration Expiration Test | None | [7 empty] | P | 20 |  |  | MA 2/18
|  |  | 6 | ITE Skip Calibration Manager on Expired Instrument | TSW_SIQT_Self_Test.xts | [7 empty] | P | 10 |  |  | RH 2/19
[5 empty] | TSW_SIQT_Self_Test.xts | [7 empty] | P |  |  |  | RH 2/19
|  |  | 7 | ITE Change Calibration Date | TSW_SIQT_Self_Test.xts | [7 empty] | P | 10 |  |  | RH 2/19
[5 empty] | TSW_SIQT_Self_Test.xts | [7 empty] | P | 10 |  |  | RH 2/19
| 2 | 3 | 1 | Script Execution MDU | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | RH 2/19
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5 |  |  | RH 2/19
|  |  | 2 | Script Execution STE | Utility_MDU_ReInitialization.xts | [7 empty] | P | 20 |  |  | RH 2/19
[5 empty] | AAAA_MDU_Set_Config_Var_Utility.xts | [7 empty] | P | 5 |  |  | RH 2/19
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts | [7 empty] | P | 5 |  |  | RH 2/19
[5 empty] | TSW_SIQT_MDU_Telemetry.xts | [7 empty] | P | 30 |  |  | RH 2/19
[5 empty] | TSW_SIQT_Prompt_Operator_MITE | [7 empty] | P | 5 |  |  | RH 2/19
|  |  | 3 | Script Control Flow and TRUE_PATH Math functions | TSW_SIQT_ScriptControlFlow.xts | [7 empty] | P | 5 |  |  | RH 2/19
|  |  | 4 | Script Control Flow and FALSE_PATH Math functions | TSW_SIQT_ScriptControlFlow.xts | [7 empty] | P | 5 |  |  | RH 2/19
|  |  | 5 | Queuing Test Scripts and data base retrieval | Utility_MDU_ReInitialization.xts | [7 empty] | P | 15 |  |  | RH 2/19
[5 empty] | AAAA_MDU_Set_Config_Var_Utility.xts | [7 empty] | P | 5 |  |  | RH 2/19
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts | [7 empty] | P | 5 |  |  | RH 2/19
[5 empty] | TSW_SIQT_TLM_n_Measurements.xts | [7 empty] | P | 10 |  |  | RH 2/19
[5 empty] | TSW_SIQT_Prompt_Operator.xts | [7 empty] | P | 5 |  |  | RH 2/19
[5 empty] | TSW_SIQT_MDU_Telemetry.xts | [7 empty] | P | 30 |  |  | RH 2/19
|  |  | 6 | Query of raw and processed data | None | [7 empty] | P | 60 |  |  | RH 2/20
|  |  | 7 | Abort Test | TSW_SIQT_Self_Test.xts | [7 empty] | P | 10 |  |  | RH 2/20
|  |  | 8 | Remote Script | TSW_SIQT_Remote_Execute_MITE.xts | [7 empty] | P | 15 |  |  | RH 2/20
|  |  | 9 | Continuous Monitor | TSW_SIQT_ContinousMonitor.xts | [7 empty] | P | 20 |  |  | RH 2/20
|  |  | 10 | TLM recorded in Database | None | [7 empty] | P | 20 |  |  | RH 2/20
|  |  | 11 | Demonstrate Ability To Select Individual Tests | TSW_SIQT_MDU_Telemetry.xts | [7 empty] | P | 30 |  |  | RH 2/20
[5 empty] | TSW_SIQT_Prompt_Operator.xts | [7 empty] | P | 5 |  |  | RH 2/20
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15 |  |  | RH 2/20
[5 empty] | TSW_SIQT_Prompt_Operator.xts | [7 empty] | P |  |  |  | RH 2/20
[5 empty] | TSW_SIQT_Sections.xts (Prompt 1) | [7 empty] | P | 5 |  |  | RH 2/20
[5 empty] | TSW_SIQT_Sections.xts (Prompt 3) | [7 empty] | P | 5 |  |  | RH 2/20
[5 empty] | TSW_SIQT_Sections.xts (Prompt 2) | [7 empty] | P | 5 |  |  | RH 2/20
| 2 | 4 | 1 | Controlled shutdown of the NPE TSW | None | [7 empty] | P | 15 |  |  | WG 2/22 updt and run
| 2 | 5 | 1 | Emergency Shutdown Function | TSW_SIQT_Emergency_Shutdown.xts | [7 empty] | P | 5 |  |  | RH 2/20
| 2 | 6 | 1 | Logging Behaviors | AAAA_MDU_Set_Config_Var_Utility.xts | [7 empty] | P | 5 |  |  | MH 3/5, BG
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts | [7 empty] | P | 5
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_MDU_Telemetry.xts | [7 empty] | P | 30
| 2 | 7 | 1 | Script Aborts on Tlm Failure | TSW_SIQT_Measurement_Check_Failures.xts | [7 empty] | P | 5 |  |  | RH 2/21
[5 empty] | TSW_SIQT_Prompt_Operator_MITE.xts | [7 empty] | P | 5
|  |  | 2 | Halts upon Measurement Check Failure | TSW_SIQT_Measurement_Check_Failures.xts | [7 empty] | P | 5 |  |  | RH 2/21
[5 empty] | TSW_SIQT_Prompt_Operator.xts | [7 empty] | P | 5
| 2 | 8 | 1 | LM Interface | None | [7 empty] | P | 30 |  |  | RH 2/22
|  |  | 2 | Testing the Heartbeat Request/Response & Monitor Msg | TSW_SIQT_EGSE_Interface.xts | [7 empty] | F | 30 |  |  | WG 3/1
[5 empty] | TSW_SIQT_EGSE_Interface.xts | [7 empty] | F | 30 |  |  | WG 3/1
|  |  | 3 | TCC Abort Script Function | TSW_SIQT_EGSE_Interface.xts | [7 empty] | F | 30 |  |  | WG 3/1
|  |  | 4 | TTC/ATP Connectivity functions to TestEngineExecutive | TSW_SIQT_TCC_TEST_Loop.xts | [7 empty] | F | 30 |  |  | WG 3/1
[5 empty] | TSW_SIQT_Prompt_Operator.xts | [7 empty] | F | 5 |  |  | WG 3/1
[5 empty] | TSW_SIQT_Prompt_Operator.xts | [7 empty] | F | 5 |  |  | WG 3/1
7.1 | 3 | 1 | 1 | Power Supply Functions | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | RH 2/22
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | STE_MDU_70V_AB_OFF_ON.xts | [7 empty] | P | 10
[5 empty] | TTCPSCNTRL.xts | [7 empty] | P | 5
[5 empty] | TTCPSCNTRL.xts | [7 empty] | P | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
|  | 1 | 2 | Prime Power Outputs | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | MH 2/24
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | TSW_SIQT_Prime_Power_Outputs.xts | [7 empty] | P | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
| 3 | 2 | 1 | Total RF Power | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | MH 2/25
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | Utility_MDU_ReInitialization.xts | [7 empty] | P | 20
[5 empty] | TSW_SIQT_MDU_Lband_Total_RF_Power.xts | [7 empty] | P | 20
|  |  | 2 | Lband Output Return Loss | TSW_MDU_Lband_Output_Return_Loss.xts | [7 empty] | P | 15 |  |  | ** check out
| 3 | 3 | 1 | TKS Allan Deviation | TSW_SIQT_MDU_TKS_Allen_Deviation.xts | [7 empty] | P | 90 |  |  | BH 2/25
|  |  | 2 | MDU VCXO Phase Noise | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | MH 3/4
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | Utility_MDU_ReInitialization.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_MDU_VCXO_TKS_Phase_Noise.xts | [7 empty] | P | 35
|  |  | 3 | AFS Signals | Utility_MDU_AFS_Setup.xts | [7 empty] | P | 15 |  |  | RH 2/22
[5 empty] | Utility_MDU_AFS_Setup.xts | [7 empty] | P | 15
[5 empty] | Utility_MDU_AFS_Setup.xts | [7 empty] | P | 15
[5 empty] | Utility_MDU_AFS_Setup.xts | [7 empty] | P | 15
|  |  | 4 | ECTS/EIE Verification | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | F | 5 |  |  | MH 2/22
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | F | 5
[5 empty] | Utility_MDU_ReInitialization.xts | [7 empty] | F | 15
[5 empty] | TSW_SIQT_SFM_NEC_Commanding.xts | [7 empty] | F | -
| 3 | 4 | 1 | Telemetry | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | WG 2/21 QA
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | Utility_MDU_ReInitialization.xts | [7 empty] | P | 15
[5 empty] | TSW_SIQT_MDU_Telemetry | [7 empty] | P | 30
|  |  | 2 | TLM verification through the EGSE Ethernet Interface | TSW_SIQT_TlmAnalog.xts | [7 empty] | F | 5 |  |  | MH 2/25 Abort due to Analyze failure
[5 empty] | TSW_SIQT_TlmDiscrete.xts | [7 empty] | F | 5
[5 empty] | TSW_SIQT_TlmSerial.xts | [7 empty] | F | 5
[5 empty] | TSW_SIQT_TlmAnalog.xts | [7 empty] | F | 5
[5 empty] | TSW_SIQT_TlmDiscrete.xts | [7 empty] | F | 5
[5 empty] | TSW_SIQT_TlmSerial.xts | [7 empty] | F | 5
| 3 | 5 | 1 | HPE Timing Signal | TSW_SIQT_MDU_HPE_Signals.xts | [7 empty] | P | 30
| 3 | 6 | 1 | Bus BDP Cmd Transaction | MDU_NDS_BDP_Commands.xts | [7 empty] | F | 10 |  |  | Message Not Found, 9129221 errors, MTH 5/3/14 measurment errors. SID 1147
|  |  | 2 | 1553 Black Bus | Utility_MDU_Reinitialization.xts | [7 empty] | F | 15 |  |  | RH 3/4 error script not valid for config 0, set config first?
[5 empty] | TSW_SIQT_Test_1553_Side.xts | [7 empty] | F | 5
[5 empty] | Utility_MDU_Reinitialization.xts | [7 empty] | F | 15
[5 empty] | TSW_SIQT_Test_1553_Side.xts | [7 empty] | F | 5
[5 empty] | Utility_MDU_Reinitialization.xts | [7 empty] | F | 15
|  |  | 3 | 1553 Inject All Telemetry | TSW_SIQT_1553_Inject_All_Telemetry.xts | [7 empty] | P | 40 |  |  | WG 2/14 QA
|  |  | 4 | SV Attitude message functions | TSW_SIQT_Test_SV_Attitude_Msg.xts | [7 empty] | P | 20 |  |  | MH 2/23
|  |  | 5 | Validate Nav Message Processing | Utility_Validate_Nav_Messages_Processing.xts | [7 empty] | P | 300 |  |  | MH 2/23
7.1 | 4 | 1 | 1 | LBCR Nominal State | MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts NPEITE: Utility_NPE_LBCR_Diddle.xts |  |  | OPTIONAL |  | OPTIONAL |  |  |  | 210
[5 empty] | MITE/MAR: Utility_Setup_Test_Transmitter_Nominal.xts NPEITE: Utility_Setup_Test_Transmitter_Nominal.xts |  |  | OPTIONAL |  | OPTIONAL |  |  |  | 30
|  |  | 2 | LBCR Self Test | MITE/MAR: Utility_MDU_ReInitialization.xts NPEITE: NPE_Configuration.xts (optional) | [5 empty] | BG? |  | ? | 20 |  |  | JF 1/24, SID 2971-2974
[5 empty] | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 5
[5 empty] | MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts NPEITE: Utility_NPE_LBCR_Diddle.xts | [8 empty] | 10
[5 empty] | MITE/MAR: TSW_SIQT_MDU_LBCR_Verification_with _TTX_with_C.xts NPEITE: TSW_SIQT_NPE_LBCR_Verification_with _TTX_with_C.xts | [8 empty] | -
|  |  | 3 | LBCR SVID Test | Utility_MDU_Reinitialization.xts | [8 empty] | 15 |  |  | team, work in progress
[5 empty] | NPEITE: NPE_Configuration.xts (optional) | [8 empty] | -
[5 empty] | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 5
[5 empty] | MDU_SVID.xts | [8 empty] | 240
|  |  | 4 | LBCR L-Band signals' correlation loss Data Acquisition Test | Utility_RF_ASSY_Manual_Control.xts | [7 empty] | P | 15 |  |  | JF 1/24, 2975
[5 empty] | MITE/MAR: NPE_Correlation_Loss.xts NPEITE: TSW_SIQT_NPE_Correlation_Loss.xts | [8 empty] | 5
| 4 | 2 | 1 | Lband In-Band Emissions | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | ? | 5 |  |  | JF 1/23
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [8 empty] | 5
[5 empty] | Utility_MDU_ReInitialization.xts | [8 empty] | 15
[5 empty] | TSW_SIQT_MDU_Lband_In-Band_Emissions.xts | [8 empty] | 130
[5 empty] | Utility_MDU_ReInitialization.xts | [8 empty] | 15
|  |  | 2 | Lband Phase Noise | Utility_MDU_ReInitialization.xts | [8 empty] | 15
[5 empty] | TSW_SIQT_MDU_Lband_Phase_Noise.xts | [8 empty] | 180
[5 empty] | Utility_MDU_ReInitialization.xts | [8 empty] | 15
|  |  | 3 | Out-of-Band Emissions | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 15 |  |  | JF 1/23, redlines, DR 3479
[5 empty] | Utility_MDU_ReInitialization.xts | [8 empty] | 20
[5 empty] | MDU_Lband_OOBE.xts | [8 empty] | 120
[5 empty] | MDU_Lband_OOBE.xts | [8 empty] | 120
[5 empty] | MDU_Lband_OOBE.xts | [8 empty] | 120
| 4 | 3 | 1 | Non Standard Code | Utility_MDU_Reinitialization.xts | [7 empty] | ? | 15 |  |  | JF 1/24, not complete
[5 empty] | MITE/MAR: TSW_SIQT_MDU_Non_Standard_Codes.xts NPEITE: TSW_SIQT_NPE_Non_Standard_Codes.xts | [8 empty] | 25
|  |  | 2 | Cross Link Transmit | MDU_Configuration.xts | [7 empty] | ? | - |  |  | JF 1/24, 2978
[5 empty] | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 5
[5 empty] | MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts NPEITE: Utility_NPE_LBCR_Diddle.xts | [8 empty] | 10
[5 empty] | NPEITE(on Config 4 only): Utility_Set_Red_Bus_Side.xts | [8 empty] | -
[5 empty] | MITE/MAR: TSW_SIQT_MDU_Crosslink_Transmit.xts NPEITE: TSW_SIQT_NPE_Crosslink_Transmit.xts | [8 empty] | 10
|  |  | 3 | Cross Link Receive | MITE/MAR: Utility_MDU_ReInitialization.xts | [7 empty] | ? | 15 |  |  | JF 1/24
NPEITE: NPE_Configuration.xts (optional)
[5 empty] | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 5
[5 empty] | MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts NPEITE: Utility_NPE_LBCR_Diddle.xts | [8 empty] | 10
[5 empty] | MITE/MAR: TSW_SIQT_MDU_Crosslink_Receive.xts NPEITE: TSW_SIQT_NPE_Crosslink_Receive.xts | [8 empty] | 10
|  |  | 4 | GED and LLED Interfaces | Utility_MDU_ReInitialization.xts | [8 empty] | 15 |  |  | MTH 6/3/2014 Pass SID 1148
[5 empty] | TSW_SIQT_MDU_GED_LLED_Events.xts | [8 empty] | 15 |  |  | MTH 6/3/2014 Pass. SID 1149
[5 empty] | Utility_MDU_ReInitialization.xts | [8 empty] | 15 |  |  | MTH 6/3/2014 Pass. SID 1150
|  |  | 5 | Transmitter Control | MITE/MAR: Utility_MDU_ReInitialization.xts NPEITE: NPE_Configuration.xts | [8 empty] | 15
[5 empty] | TSW_SIQT_MDU_Transmitter_Control_Word.xts | [8 empty] | 75
|  |  | 6 | Code Dwell Imbalance | Utility_MDU_ReInitialization.xts | [8 empty] | 15
[5 empty] | MDU_Code_Dwell_Imbalance.xts | [8 empty] | 5
|  |  | 7 | MDU X1 Epoch Adjust | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) | [8 empty] | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [8 empty] | 5
[5 empty] | TSW_SIQT_MDU_X1_Epoch_Adjust.xts | [8 empty] | 15
|  |  | 8 | Key Supercession | NPEITE: A_npe_key_scheduling_scenarios_1_to_4.xts MITE: A_MDU_key_scheduling_scenarios_1_to_4.xts | [7 empty] | P | 20 |  |  | JF 1/25, SID 226
7.1 | 5 | 1 | 1 | MDU Hard Reset Bootstrap | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 1 |  |  | RH 2/24
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 1
[5 empty] | TSW_SIQT_Hard_Reset_Bootstrap.xts | [7 empty] | P | 10
|  |  | 2 | Soft Reset the Boot Software | TSW_SIQT_Soft_Reset_Bootstrap.xts | [7 empty] | P | 10 |  |  | RH 2/24
| 5 | 2 | 1 | Stored Command Status | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | RH 2/24
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | TSW_SIQT_Stored_Commands.xts | [7 empty] | P | 5
| 5 | 3 | 1 | Boot Invalid Serial Command Status | BOOT_MDU_Power_OnOff.xts(OFF) | [7 empty] | P | 5
[5 empty] | BOOT_MDU_Power_OnOff.xts(ON) | [7 empty] | P | 5
[5 empty] | TSW_SIQT_Invalid_SMCs.xts | [7 empty] | P | 40
|  |  | 2 | CCAs and Stored Commands | BOOT_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5
[5 empty] | BOOT_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | TSW_SIQT_CCAs_and_Stored_Commands.xts | [7 empty] | P | 10
|  |  | 3 | Valid Commands | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | F | 5 |  |  | RH 2/24 1255-1291 not present
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | F | 5
[5 empty] | TSW_SIQT_Valid_Commands.xts | [7 empty] | F | 5
[5 empty] | TSW_SIQT_Reserved_SMCs.xts | [7 empty] | F | 60
| 5 | 4 | 1 | Valid MUB | TSW_SIQT_Upload_Nominal_MUBs.xts | [7 empty] | F | 10 |  |  | RH 2/24 1255-1291 not present
[5 empty] | TSW_SIQT_Upload_Nominal _MUB.time.xts | [7 empty] | F | 10
|  |  | 2 | Invalid MUB | TSW_SIQT_Invalid_Checksum.xts | [7 empty] | P | 10 |  |  | RH 2/24
|  |  | 3 | Too Large MUB | TSW_SIQT_Too_Large.xts | [7 empty] | P | 10 |  |  | RH 2/24
| 5 | 5 | 1 | SRAM Fill Pattern Diagnostics Dump Telemetry | BOOT_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5 |  |  | RH 2/24
[5 empty] | BOOT_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
[5 empty] | TSW_SIQT_Fill_Pattern _Dump_Telemetry.xts | [7 empty] | P | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | P | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | P | 5
7.1 | 6 |  |  | Analysis | [12 empty] | Analysis |  |  |  |  | In Process | Will be Completed Post SIQT
6 | 24 | 25 | 89 | Test Execution(Does not include Analysis) | 198 | 216 | 216 |  |  | 0 |  |  | 0 | 3987 |  | 0
Test Cases | Test Sub Cases | Test Sect. | Test Groups |  | 18 | [16 empty] | Task Status Legend:
Needs examination
[5 empty] | ExecutionStatus legend: | [10 empty] | #DIV/0! | [5 empty] | Work identified and in progress
[5 empty] | Pass = Passed execution and verification. | [7 empty] | 0 | [8 empty] | Reviewed, Ready for Test
[5 empty] | EX = Unable to execute due to procedure or script issue. Cannot determine verification. | [7 empty] | 0
Fail = Failed verification.
[5 empty] | SWIT Run Status |  | Total Script Executions Planned | Total Script Executions | % Scripts Run | Total Test Case | Passed | Test Case Passed | Test Case Failed | Test Case Execution Issue |  |  | Test Case N/A
[5 empty] | Total Test Scripts |  | 198 | 216 | 0% | 216 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | Scripts Executed |  | 216 | 0
[5 empty] | Not Including Analysis |  | 6
[5 empty] | TestCases |  | 25 | 6
[5 empty] | Total Test Subcases |  | 89 | 24
[5 empty] | Total Sections |  |  | 25
|  |  |  | List of test scripts are based on following versions of test cases | Test Case |  | TSW Test Case | Subcase | Scripts | TC | Total Pass | EX | Pass | Failed | Execution Issue
|  |  |  | TC01, ver 51 | 7.1.1.1 |  | 1 | 1 | 10 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | TC02, ver 87 | 7.1.1.2 |  | 2 | 1 | 15 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | TC03, ver 119 |  |  | 2 | 2 | 9 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | TC04, ver 111 |  |  | 2 | 3 | 27 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | TC05, ver 58 |  |  | 2 | 4 | 1 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 2 | 5 | 1 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 2 | 6 | 11 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 2 | 7 | 4 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 2 | 8 | 7 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 7.1.1.3 |  | 3 | 1 | 12 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 3 | 2 | 5 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 3 | 3 | 13 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 3 | 4 | 10 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 3 | 5 | 1 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 3 | 6 | 9 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 7.1.1.4 |  | 4 | 1 | 11 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 4 | 2 | 10 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 4 | 3 | 23 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 7.1.1.5 |  | 5 | 1 | 4 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 5 | 2 | 3 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 5 | 3 | 10 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 5 | 4 | 4 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 7.1.1.6 |  | 6 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0
[9 empty] | 205 |  | 0 | 0 | 0 | 0 | 0 |  |  | Sanity Check

## MasterScriptList
AAAA_MDU_Set_Config_Var_Utility.xts | AAAA_MDU_Set_Config_Var_Utility.xts | AAAA_MDU_Set_Config_Var_Utility.xts
AAAA_MDU_Set_OpMode_Var_Utility.xts | AAAA_MDU_Set_OpMode_Var_Utility.xts | AAAA_MDU_Set_OpMode_Var_Utility.xts
BOOT_MDU_Power_OnOff.xts (OFF/ON) | BOOT_MDU_Power_OnOff.xts (OFF/ON) | BOOT_MDU_Power_OnOff.xts (OFF/ON)
for SWIT: Utility_Validate_Nav_Messages_Processing_For_SWIT_Start.xts for SIQT: Utility_Validate_Nav_Messages_Processing.xts | for SWIT: Utility_Validate_Nav_Messages_Processing_For_SWIT_Start.xts for SIQT: Utility_Validate_Nav_Messages_Processing.xts | for SWIT: Utility_Validate_Nav_Messages_Processing_For_SWIT_Start.xts for SIQT: Utility_Validate_Nav_Messages_Processing.xts
MDU_Code_Dwell_Imbalance.xts | MDU_Code_Dwell_Imbalance.xts | MDU_Code_Dwell_Imbalance.xts
MDU_Configuration.xts | MDU_Configuration.xts | MDU_Configuration.xts
MDU_Lband_OOBE.xts | MDU_Lband_OOBE.xts | MDU_Lband_OOBE.xts
MDU_NDS_BDP_Commands.xts | MDU_NDS_BDP_Commands.xts | MDU_NDS_BDP_Commands.xts
MDU_SVID.xts | MDU_SVID.xts | MDU_SVID.xts
MITE/MAR: NPE_Correlation_Loss.xts NPEITE: TSW_SIQT_NPE_Correlation_Loss.xts | MITE/MAR: NPE_Correlation_Loss.xts | NPEITE: TSW_SIQT_NPE_Correlation_Loss.xts
MITE/MAR: TSW_SIQT_MDU_Crosslink_Receive.xts NPEITE: TSW_SIQT_NPE_Crosslink_Receive.xts | MITE/MAR: TSW_SIQT_MDU_Crosslink_Receive.xts | NPEITE: TSW_SIQT_NPE_Crosslink_Receive.xts
MITE/MAR: TSW_SIQT_MDU_Crosslink_Transmit.xts NPEITE: TSW_SIQT_NPE_Crosslink_Transmit.xts | MITE/MAR: TSW_SIQT_MDU_Crosslink_Transmit.xts | NPEITE: TSW_SIQT_NPE_Crosslink_Transmit.xts
MITE/MAR: TSW_SIQT_MDU_LBCR_Verification_with _TTX_with_C.xts NPEITE: TSW_SIQT_NPE_LBCR_Verification_with _TTX_with_C.xts | MITE/MAR: TSW_SIQT_MDU_LBCR_Verification_with _TTX_with_C.xts | NPEITE: TSW_SIQT_NPE_LBCR_Verification_with _TTX_with_C.xts
MITE/MAR: TSW_SIQT_MDU_Non_Standard_Codes.xts NPEITE: TSW_SIQT_NPE_Non_Standard_Codes.xts | MITE/MAR: TSW_SIQT_MDU_Non_Standard_Codes.xts | NPEITE: TSW_SIQT_NPE_Non_Standard_Codes.xts
MITE/MAR: Utility_MDU_ReInitialization.xts | Utility_MDU_ReInitialization.xts | Utility_MDU_ReInitialization.xts
MITE/MAR: Utility_MDU_ReInitialization.xts NPEITE: NPE_Configuration.xts |  | NPEITE: NPE_Configuration.xts
MITE/MAR: Utility_Setup_Test_Transmitter_Nominal.xts NPEITE: Utility_Setup_Test_Transmitter_Nominal.xts | Utility_Setup_Test_Transmitter_Nominal.xts | MITE/MAR: Utility_Setup_Test_Transmitter_Nominal.xts NPEITE: Utility_Setup_Test_Transmitter_Nominal.xts
MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts NPEITE: Utility_NPE_LBCR_Diddle.xts | MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts | MITE/MAR: Utility_TSW_SIQT_MDU_LBCR_Diddle.xts NPEITE: Utility_NPE_LBCR_Diddle.xts
NPEITE(on Config 4 only): Utility_Set_Red_Bus_Side.xts |  | NPEITE(on Config 4 only): Utility_Set_Red_Bus_Side.xts
NPEITE: A_npe_key_scheduling_scenarios_1_to_4.xts MITE: A_MDU_key_scheduling_scenarios_1_to_4.xts | MITE: A_MDU_key_scheduling_scenarios_1_to_4.xts | NPEITE: A_npe_key_scheduling_scenarios_1_to_4.xts
NPEITE: NPE_Configuration.xts (optional) | NPEITE: NPE_Configuration.xts (optional) | NPEITE: NPE_Configuration.xts (optional)
STE_MDU_70V_AB_OFF_ON.xts | STE_MDU_70V_AB_OFF_ON.xts | STE_MDU_70V_AB_OFF_ON.xts
TSW_MDU_Lband_Output_Return_Loss.xts | TSW_MDU_Lband_Output_Return_Loss.xts | TSW_MDU_Lband_Output_Return_Loss.xts
TSW_SIQT_1553_Inject_All_Telemetry.xts | TSW_SIQT_1553_Inject_All_Telemetry.xts | TSW_SIQT_1553_Inject_All_Telemetry.xts
TSW_SIQT_Bad_Syntax.xts | TSW_SIQT_Bad_Syntax.xts | TSW_SIQT_Bad_Syntax.xts
TSW_SIQT_Calibration_MAR.xts | TSW_SIQT_Calibration_MAR.xts | TSW_SIQT_Calibration_MAR.xts
TSW_SIQT_CCAs_and_Stored_Commands.xts | TSW_SIQT_CCAs_and_Stored_Commands.xts | TSW_SIQT_CCAs_and_Stored_Commands.xts
TSW_SIQT_ContinousMonitor.xts | TSW_SIQT_ContinousMonitor.xts | TSW_SIQT_ContinousMonitor.xts
TSW_SIQT_Create_and_Store_Calibration_Data.xts | TSW_SIQT_Create_and_Store_Calibration_Data.xts | TSW_SIQT_Create_and_Store_Calibration_Data.xts
TSW_SIQT_EGSE_Interface.xts | TSW_SIQT_EGSE_Interface.xts | TSW_SIQT_EGSE_Interface.xts
TSW_SIQT_Emergency_Shutdown.xts | TSW_SIQT_Emergency_Shutdown.xts | TSW_SIQT_Emergency_Shutdown.xts
TSW_SIQT_Fill_Pattern _Dump_Telemetry.xts | TSW_SIQT_Fill_Pattern _Dump_Telemetry.xts | TSW_SIQT_Fill_Pattern _Dump_Telemetry.xts
TSW_SIQT_Hard_Reset_Bootstrap.xts | TSW_SIQT_Hard_Reset_Bootstrap.xts | TSW_SIQT_Hard_Reset_Bootstrap.xts
TSW_SIQT_Invalid_Checksum.xts | TSW_SIQT_Invalid_Checksum.xts | TSW_SIQT_Invalid_Checksum.xts
TSW_SIQT_Invalid_SMCs.xts | TSW_SIQT_Invalid_SMCs.xts | TSW_SIQT_Invalid_SMCs.xts
TSW_SIQT_MDU_GED_LLED_Events.xts | TSW_SIQT_MDU_GED_LLED_Events.xts | TSW_SIQT_MDU_GED_LLED_Events.xts
TSW_SIQT_MDU_HPE_Signals.xts | TSW_SIQT_MDU_HPE_Signals.xts | TSW_SIQT_MDU_HPE_Signals.xts
TSW_SIQT_MDU_Lband_In-Band_Emissions.xts | TSW_SIQT_MDU_Lband_In-Band_Emissions.xts | TSW_SIQT_MDU_Lband_In-Band_Emissions.xts
TSW_SIQT_MDU_Lband_Phase_Noise.xts | TSW_SIQT_MDU_Lband_Phase_Noise.xts | TSW_SIQT_MDU_Lband_Phase_Noise.xts
TSW_SIQT_MDU_Lband_Total_RF_Power.xts | TSW_SIQT_MDU_Lband_Total_RF_Power.xts | TSW_SIQT_MDU_Lband_Total_RF_Power.xts
TSW_SIQT_MDU_Telemetry.xts | TSW_SIQT_MDU_Telemetry.xts | TSW_SIQT_MDU_Telemetry.xts
TSW_SIQT_MDU_TKS_Allen_Deviation.xts | TSW_SIQT_MDU_TKS_Allen_Deviation.xts | TSW_SIQT_MDU_TKS_Allen_Deviation.xts
TSW_SIQT_MDU_Transmitter_Control_Word.xts | TSW_SIQT_MDU_Transmitter_Control_Word.xts | TSW_SIQT_MDU_Transmitter_Control_Word.xts
TSW_SIQT_MDU_VCXO_TKS_Phase_Noise.xts | TSW_SIQT_MDU_VCXO_TKS_Phase_Noise.xts | TSW_SIQT_MDU_VCXO_TKS_Phase_Noise.xts
TSW_SIQT_MDU_X1_Epoch_Adjust.xts | TSW_SIQT_MDU_X1_Epoch_Adjust.xts | TSW_SIQT_MDU_X1_Epoch_Adjust.xts
TSW_SIQT_Measurement_Check_Failures.xts | TSW_SIQT_Measurement_Check_Failures.xts | TSW_SIQT_Measurement_Check_Failures.xts
TSW_SIQT_OS_Services_NotLoaded_TLM_Test.xts | TSW_SIQT_OS_Services_NotLoaded_TLM_Test.xts | TSW_SIQT_OS_Services_NotLoaded_TLM_Test.xts
TSW_SIQT_Prime_Power_Outputs.xts | TSW_SIQT_Prime_Power_Outputs.xts | TSW_SIQT_Prime_Power_Outputs.xts
TSW_SIQT_Prompt_Operator.xts | TSW_SIQT_Prompt_Operator.xts | TSW_SIQT_Prompt_Operator.xts
TSW_SIQT_Prompt_Operator_MAR.xts | TSW_SIQT_Prompt_Operator_MAR.xts | TSW_SIQT_Prompt_Operator_MAR.xts
TSW_SIQT_Prompt_Operator_MITE.xts | TSW_SIQT_Prompt_Operator_MITE.xts | TSW_SIQT_Prompt_Operator_MITE.xts
TSW_SIQT_Remote_Execute_MITE.xts | TSW_SIQT_Remote_Execute_MITE.xts | TSW_SIQT_Remote_Execute_MITE.xts
TSW_SIQT_Reserved_SMCs.xts | TSW_SIQT_Reserved_SMCs.xts | TSW_SIQT_Reserved_SMCs.xts
TSW_SIQT_ScriptControlFlow.xts | TSW_SIQT_ScriptControlFlow.xts | TSW_SIQT_ScriptControlFlow.xts
TSW_SIQT_Sections.xts | TSW_SIQT_Sections.xts | TSW_SIQT_Sections.xts
TSW_SIQT_Self_Test.xts | TSW_SIQT_Self_Test.xts | TSW_SIQT_Self_Test.xts
TSW_SIQT_SFM_NEC_Commanding.xts | TSW_SIQT_SFM_NEC_Commanding.xts | TSW_SIQT_SFM_NEC_Commanding.xts
TSW_SIQT_Soft_Reset_Bootstrap.xts | TSW_SIQT_Soft_Reset_Bootstrap.xts | TSW_SIQT_Soft_Reset_Bootstrap.xts
TSW_SIQT_Stored_Commands.xts | TSW_SIQT_Stored_Commands.xts | TSW_SIQT_Stored_Commands.xts
TSW_SIQT_TCC_TEST_Loop.xts | TSW_SIQT_TCC_TEST_Loop.xts | TSW_SIQT_TCC_TEST_Loop.xts
TSW_SIQT_Test_1553_Side.xts | TSW_SIQT_Test_1553_Side.xts | TSW_SIQT_Test_1553_Side.xts
TSW_SIQT_Test_SV_Attitude_Msg.xts | TSW_SIQT_Test_SV_Attitude_Msg.xts | TSW_SIQT_Test_SV_Attitude_Msg.xts
TSW_SIQT_TLM_n_Measurements.xts | TSW_SIQT_TLM_n_Measurements.xts | TSW_SIQT_TLM_n_Measurements.xts
TSW_SIQT_TlmAnalog.xts | TSW_SIQT_TlmAnalog.xts | TSW_SIQT_TlmAnalog.xts
TSW_SIQT_TlmDiscrete.xts | TSW_SIQT_TlmDiscrete.xts | TSW_SIQT_TlmDiscrete.xts
TSW_SIQT_TlmSerial.xts | TSW_SIQT_TlmSerial.xts | TSW_SIQT_TlmSerial.xts
TSW_SIQT_TlmSerial_fail.xts | TSW_SIQT_TlmSerial_fail.xts | TSW_SIQT_TlmSerial_fail.xts
TSW_SIQT_Too_Large.xts | TSW_SIQT_Too_Large.xts | TSW_SIQT_Too_Large.xts
TSW_SIQT_Upload_Nominal _MUB.time.xts | TSW_SIQT_Upload_Nominal _MUB.time.xts | TSW_SIQT_Upload_Nominal _MUB.time.xts
TSW_SIQT_Upload_Nominal_MUBs.xts | TSW_SIQT_Upload_Nominal_MUBs.xts | TSW_SIQT_Upload_Nominal_MUBs.xts
TSW_SIQT_Valid_Commands.xts | TSW_SIQT_Valid_Commands.xts | TSW_SIQT_Valid_Commands.xts
TTCPSCNTRL.xts | TTCPSCNTRL.xts | TTCPSCNTRL.xts
Utility_MDU_AFS_Setup.xts | Utility_MDU_AFS_Setup.xts | Utility_MDU_AFS_Setup.xts
Utility_MDU_Power_OnOff.xts | Utility_MDU_Power_OnOff.xts | Utility_MDU_Power_OnOff.xts
Utility_MDU_ReInitialization.xts | Utility_MDU_ReInitialization.xts | Utility_MDU_ReInitialization.xts
Utility_MDU_Software_Version.xts | Utility_MDU_Software_Version.xts | Utility_MDU_Software_Version.xts
Utility_RF_ASSY_Manual_Control.xts | Utility_RF_ASSY_Manual_Control.xts | Utility_RF_ASSY_Manual_Control.xts
| MM1 | NPE

## SIRN installed
date | CSTS SIRN 11796 | LBCR SIRN
as 3/5/14 | BG | SIRN11853K_eng_2.0_SECRET