## Sheet1
Details/Resolution | POC | Due date | Resolution | Complete Date
LM to provide working copy of SRS and IRS to update requirements. | David | 2014-01-31 | Received SRS and IRS export from LM. | Closed TR 1/31/2014
TC02 section 2.2.1: Re-examine 2.2.1 and restore redlines (21, 22, 23) if needed. | Hamida | 2014-01-31 | Restored Subcase back to original state. | Closed HY 1/31/14
Remove all “Deleted” lines from bottom of test case procedures. | Hamida | 2014-01-31 | Opened all files and confirmed the DELETED section are removed. | Closed HY 1/31/14
TC01:Check naming conventions for FEP. | Julie | 2014-01-31 | OBE - Action Item #27 After speaking with Julie on phone to visually confirm PC name , I added note to the top of the procedure under General Operation Test Guidelines NOTE: If on the NPEITE: the associated LBCR names are FEP_1_NPE, FEP_2_NPE, and FEP_CTRL_NPE | Closed HY 1/30/14
Check that script “TSW_SIQT_1553_Inject_All_Telemetry.xts” script name is correct. Believe that this has been renamed to Utility_1553_Inject_All_Telemetry.xts Need to double check with H. Yaniero. | Tricia | 2014-01-31 | The original script was to Utility_1553_Inject_All_Telemetry.xts. For testing, both the script and procedure were changed to“TSW_SIQT_1553_Inject_All_Telemetry.xts”. No further change needed. | Closed TR 1/30/2014
Fix requirement traces for Key Supercession (4265 & 3693). | Tricia | 2014-01-31 | Removed traces to SRS-3697, 3698, 3699 and 3700. The copy of 3693 was dragged down and the requirement number incremented. Traced Key Supercession test procedure to SRS-4265 and SRS-3693. | Closed TR 1/31/2014
Move scripts from NPEITE1 to MM3 | Andrea | 2014-02-03
TC04 section 4.3.7 (X1 Epoch): Identify scripts that are needed to get this to a known, good state. (OFF/ON to replace reinit) | Hamida | 2014-02-03 | Removed Reint script and added Utility OFF and ON. Added a prerequisite line to have Tester confirm TIC before starting test. If Instrument has not been, they must find a Test Engineer. | Closed HY 1/31/14
TC01: Record host names at beginning of TC1. Remove all specific computer name references in all procedures. | Hamida | 2014-02-03 | Added list to Front of TC1 procedure under, General Operation Test Guidelines If on the NPEITE: the associated LBCR names are FEP_1_NPE, FEP_2_NPE, and FEP_CTRL_NPE the associated NPEITE: name: NPEITE_CTRL the associated TAR name: TAR_CTRL If on the MM1: the associated LBCR names are FEP_1, FEP_2, and FEP_CTRL the associated MITE name: MITE_CTRL the associated MAR name: MAR_CTRL If on the MM2: the associated LBCR names are FEP_1, FEP_2, and FEP_CTRL the associated MITE name: MITE_CTRL the associated MAR name: MAR_CTRL If on the MM3: the associated LBCR names are LBCR3_FEP1, LBCR3_FEP2, and LBCR3_CTRL the associated MITE name: MITE3_CTRL the associated MAR name: MAR3_CTRL If on the MM4: the associated LBCR names are LBCR4_FEP1, LBCR4_FEP2, and LBCR4_CTRL the associated MITE name: MITE4 the associated MAR name: MAR4 | Closed HY 1/31/14
TC04: Update LBCR pre-requisite to match line 591. | Julie | 2014-02-03 | Updated | Closed jaf 1/31/2014
TC01 section 7.1.1.1.5d: Add steps for a new SIRN. | Ken | 2014-02-03
TC02 section 2.2.8: Review subcase 2.2.8. Confirm test case is necessary and steps are correct. | Ken | 2014-02-03
TC03 section 3.4.1 MDU_Telemetry: Separate analog and discrete telemetry. Rewrite verify statements. Ensure all messages are listed. | Hamida | 2014-02-03 |  | worked on hard copy still needs to be transferred to locked down version, HY 2/04/14 Moved to original as per Trica's request. Closed 2/7/14
Ensure NPEITE Install Data Set SIRN Deployment procedure is added to the system install document. | Ken | 2014-02-03
Setup peer review of analysis procedure (TC6) | Mark M. | 2014-02-03
B2 Changes | Mary | 2014-02-03
Updates to SRS and IRS - post for LM to update DOORS | Tricia | 2014-02-03
Correct test case numbering throughout test procedures. Ensure any references to test case/subcase numbers in test steps are updated as well. | Hamida | 2014-02-04 | Did a search through each test case and verified references and checked # sequence. | Closed HY 1/31/14
Reconcile redline 24. | Hamida | 2014-02-04 | This was done during the MEETING with the customer. Tester was not reading the test correctly. The description of the test has been updated to provide more clarity. | Closed HY 2/04/14
TC02 line 221: Per redline 49, update with items taken from screenshot. | Hamida | 2014-02-05 | Corrected procedure to say what is really displayed on the TestEngine Executive and also the ITT_Debug.Log as per the Screen shot taken during SIQT. | Closed HY 1/31/14
Confirm naming of MICE variable from redline 77. Should this be MiceData or MicePath? | Julie | 2014-02-05
TC04: Review LBCR procedure for startup and recovery. Decide if this needs to be broken up into optional procedures. | Julie | 2014-02-05
Per redline 50, examine log file and reword verification statement. | Willie | 2014-02-05 | Emailed P. Roeland the updates | Closed WG 2/6/14
Decide on where to set the state – the beginning of the test or the end of the test. | Roger | 2014-02-05 | The Configuration for any test case/sub case will be set in the beginning of the test case/sub case. The configurations states may be optional but must explicitly identify the criteria it may be skipped. | Closed RM 1/31/14
Meeting between LM and Exelis to go through requirement placement in test case. (Thorough review). IRS-1282 and 1378 need some extra attention. | Tricia | 2014-02-05
Exercise installation instructions | Willie | 2014-02-05 | Completed | Closed WG 2/7/14
Review test steps that have a PASS/FAIL in all procedures. Decide on placement of PASS/FAIL (test step, subcase, test case). | Hamida | 2014-02-06 | Restored Subcase back to original state BY REMOVING PASS/FAILED CRITERIA. | Closed HY 1/31/14
Check naming conventions for MITE/NPEITE and MAR/TAR in all procedures. We must specify “If on a MITE/MAR…” and “If on a NPEITE/TAR…”. We should also ensure that script names refer to correct EGSE. | Julie | 2014-02-06 |  | Changed all Test case to use TC1 as references. I changed TC4 to meet naming convention as per this Action only when calling a specific script. All others are referenced to look at TC1 to confirm the naming convention. The generic name for a MITE or NPEITE is ITE. and a MAR or TAR is AR. this is used through all the test cases to avoid repetition. As I stated above if the specific STE requires a specific script at that point I defined it in the step. Closed HY 2/9/14
TC01 lines 51 – 53: Clarify steps for ensuring a clean database. | Ken | 2014-02-06 | Went to Jason Jackson and he gave me the correct steps to add to the procedure. Tables to run from the database and confirm they are empty: dbo.ScriptRun dbo.Results updated procedure. | Closed HY 1/30/14
Add details for verifying ITT_Debugging.log to reference document. | Roger | 2014-02-06
Ensure all requirements map to a test eval step. Test Evals with “Verify” should have an associated requirement. Test Evals with “Confirm” should not have an associated requirement. | Tricia | 2014-02-06
TC04 line 1122 and following lines, section 4.3.4: These are worded with “Verify” rather than “Confirm”. Check if requirements need to be flowed there. | Tricia | 2014-02-06
SQA Signoff on Dry Run Redline Peer Review | Cheryl | 2014-02-07
Add NPEITE STE recovery procedure to reference document. Ensure we remove instances of NPE_Config where it is not needed. | Julie | 2014-02-07
TC04 line 1167: This starts with the number 2. Ensure document text is not missing. | Hamida | 2014-02-07 | Verified through the Test Case and no documentation is missing. Re# doc text . | Closed HY 2/04/14
Add LBCR Diddle after first LBCR login in reference document. | Ken | 2014-02-07
Close out Dry Run Redline Peer Review | Ken | 2014-02-07
TC02 lines 1560 and 1561: Specific details are needed for verification. 1560 Examine the database and verify that the - UUT currents at time of failure are recorded - RF power in at time of failure are recorded - commands sent prior to time of failure are recorded - telemetry at time of failure are recorded - instrument settings at time of failure are recorded 1561 Examine the script report generated and verify as noted above for failure documentation. - UUT currents at time of failure are recorded - RF power in at time of failure are recorded - commands sent prior to time of failure are recorded - telemetry at time of failure are recorded - instrument settings at time of failure are recorded | Roger | 2014-02-07 | Note: 1560 and 1561 are now 1619 and 1620 after the completion of previous redlines. 1560 and 1561 are duplicates so removed 1561(1620). SRS and B2 requirements scope differences. Updated validation criteria to meet the B2 Flow Down requirements. This will be included in the Separate SRS/IRS tracing activities. | Closed RM 1/31/14
Debug scripts on MM3 | All | 2014-02-07
SFM Issues | Roger | 2014-02-07