## Status
STD Appendix # | TSW Test case | Sub case | section | Title | Scripts Executed | CC Version of Script Executed | planned Run Date | Test Operator | Witness | actual run date | SIRN Run On | Script Run ID | Run Status P/F | Estimated duration (minutes) | proc edits made | ready for dry run | Comments / related DR's with status | Re-run Status | Re-run Operator | Re-run Date | Estimated Hours to Completion for Review | Task Status Redlines Script Update Procedure Update Action DR Review | Notes | LM/Aero Reviewer | Accept/ Reject | Comment
If tester does not understand these, read Use Case (VOB Systems in Clear Case ) and confirm requirements are covered in the Test Case. Verify GUI Screen Shot on STD matches GUI current SIRN display.
7.1 | 1 | 1 | 1 | Initial Setup | None |  |  | H. Yaniero |  | 2014-01-21 |  |  | Pass | 5 |  |  | DR 3467 - CAT4 - Startup issue | [5 empty] | Known Issue - Add to reference document
|  |  | 2 | Confirm TSW (desktop shortcuts) | None |  |  | H. Yaniero |  | 2014-01-24 |  |  | Pass | 20
|  |  | 3 | Confirm SQL Sever Management Studio is avaliable on the PC. | None |  |  | H. Yaniero |  | 2014-01-21 |  |  | Pass | 1
|  |  | 4 | Power on and configuration verification. | None |  |  | H. Yaniero |  | 2014-01-21 |  |  | Pass | 1
|  |  | 5 | Record SIRN ID for the TSW being used for TSW SIQT. | Utility_MDU_Software_Version.xts |  |  | J. Fazio |  | 2014-01-21 |  |  | Pass | 25
|  |  | 6 | Record and confirm test directory (root) is established for SIQT. | None | [7 empty] | EX | 5 |  |  | Procedure issues, require re-write or removal. These steps may take place during installation.
|  |  | 7 | Configure MDU and STE to a "Nominal" operational state. | Utility_MDU_Power_OnOff.xts (OFF) |  |  | J. Fazio |  | 2014-01-21 |  |  | Pass | 10
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | J. Fazio |  | 2014-01-21 |  |  | Pass | 5
[5 empty] | MDU_Configuration.xts |  |  | J. Fazio |  | 2014-01-21 |  |  | Pass | 1 |  |  | DR3470 - Redline to Procedure/Script change is required
|  |  | 8 | Optional: Used during testing to do a Soft Reset to the MDU. | Utility_MDU_Reinitialization.xts |  |  | OPTIONAL |  | OPTIONAL |  |  | N/A | 15 |  |  | OPTIONAL
|  |  | 9 | Optional: Used for restoring STE to a nominal working state. | Utility_MDU_Power_OnOff.xts (OFF) |  |  | OPTIONAL |  | OPTIONAL |  |  | N/A | 5 |  |  | OPTIONAL
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | OPTIONAL |  | OPTIONAL |  |  | N/A | 5 |  |  | OPTIONAL
7.1 | 2 | 1 | 1 | Nominal State | None |  |  | W. Guan |  | 2014-01-24 |  |  | Pass | 30
|  |  | 2 | Establish AR Control | TSW_SIQT_Bad_Syntax.xts |  |  | J. Fazio |  | 2014-01-21 |  |  | Pass | 15
|  |  | 3 | Prompt Operator from AR STE | TSW_SIQT_Prompt_Operator_MAR.xts |  |  | J. Fazio |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TlmSerial_fail.xts |  |  | J. Fazio |  | 2014-01-22 |  |  | Pass | 40
|  |  | 4 | Restore ITE Control | None | [7 empty] | Pass | 5 |  |  | DR3469
|  |  | 5 | Prompt Operator from ITE STE | TSW_SIQT_Prompt_Operator.xts | [7 empty] | EX | 5 |  |  | DR3471 Need to rewrite verify for this test and re-test.
|  |  | 6 | Detection of Faults at Startup | None | [7 empty] | EX | 20 |  |  | Need to verify if this Test Eval should be a 48 or a 0. There was confusion regardig this test eval. The 48 was part of a referenced piece of log file and does not effect the test. Need to re-write verify to make more clear and rerun. No data saved.
|  |  | 7 | Detection of disconnected cable from STE | None |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 15
|  |  | 8 | Disconnected AR Ethernet cable | None |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 15
|  |  | 9 | AR Instrument Power Down detected by ITE | TSW_SIQT_Self_Test.xts |  |  | M. Anna |  | 2014-01-22 |  |  | EX | 10 |  |  | Needs further verification of non-matching numbers.
|  |  | 10 | Process Startup-Shutdown | AAAA_MDU_Set_Config_Var_Utility.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | TSW_SIQT_OS_Services_NotLoaded_TLM_Test.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 10
|  |  | 11 | Invalid Startup Configurations | None |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 25
|  |  | 12 | Detect Invalid Configuration With Missing Configuration File | None |  |  | M. Anna |  | 2014-01-22 |  |  | EX | 15 |  |  | Needs data review to verify results.
| 2 | 2 | 1 | Test Software configuration files | TSW_SIQT_Prompt_Operator.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 5
|  |  | 2 | ITE Primary Controller of AR | TSW_SIQT_Calibration_MAR.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 15
|  |  | 3 | AR Test Configuration Data | None |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 20 |  |  | DR3469
|  |  | 4 | AR Calibration Expiration Test | None |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 28 |  |  | DR3469
|  |  | 5 | ITE Calibration Expiration Test | None |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 20
|  |  | 6 | ITE Skip Calibration Manager on Expired Instrument | TSW_SIQT_Self_Test.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 10
|  |  | 7 | ITE Change Calibration Date | TSW_SIQT_Self_Test.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 10
[5 empty] | TSW_SIQT_Self_Test.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 10
|  |  | 8 | ITE Verification of STE Folders | None |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 8
| 2 | 3 | 1 | Script Execution MDU | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
|  |  | 2 | Script Execution STE | Utility_MDU_ReInitialization.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 20
[5 empty] | AAAA_MDU_Set_Config_Var_Utility.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | TSW_SIQT_MDU_Telemetry.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 30
[5 empty] | TSW_SIQT_Prompt_Operator_MITE |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
|  |  | 3 | Script Control Flow and TRUE_PATH Math functions | TSW_SIQT_ScriptControlFlow.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
|  |  | 4 | Script Control Flow and FALSE_PATH Math functions | TSW_SIQT_ScriptControlFlow.xts |  |  | H. Yaniero |  | 2014-01-22 |  |  | Pass | 5
|  |  | 5 | Queuing Test Scripts and data base retrieval | Utility_MDU_ReInitialization.xts |  |  | W. Guan |  | 2014-01-22 |  |  | Pass | 15
[5 empty] | AAAA_MDU_Set_Config_Var_Utility.xts |  |  | W. Guan |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts |  |  | W. Guan |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TLM_n_Measurements.xts |  |  | W. Guan |  | 2014-01-22 |  |  | Pass | 10
[5 empty] | TSW_SIQT_Prompt_Operator.xts |  |  | W. Guan |  | 2014-01-22 |  |  | Pass | 5
[5 empty] | TSW_SIQT_MDU_Telemetry.xts |  |  | W. Guan |  | 2014-01-22 |  |  | Pass | 30
|  |  | 6 | Query of raw and processed data | None |  |  | M. Hazel |  | 2014-01-22 |  |  | Pass | 60
|  |  | 7 | Abort Test | TSW_SIQT_Self_Test.xts |  |  | M. Hazel |  | 2014-01-22 |  |  | Pass | 10
|  |  | 8 | Remote Script | TSW_SIQT_Remote_Execute_MITE.xts |  |  | M. Hazel |  | 2014-01-22 |  |  | Pass | 15
|  |  | 9 | Continuous Monitor | TSW_SIQT_ContinousMonitor.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 20
|  |  |  | TLM_OFF_ON Function | TSW_SIQT_TLM_OFF_ON.xts |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 20
|  |  | 10 | TLM recorded in Database | None |  |  | M. Anna |  | 2014-01-22 |  |  | Pass | 20
|  |  | 11 | Demonstrate Ability To Select Individual Tests | TSW_SIQT_MDU_Telemetry.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30
[5 empty] | TSW_SIQT_Prompt_Operator.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Sections.xts (Prompt 1) |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Sections.xts (Prompt 3) |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Sections.xts (Prompt 2) |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
| 2 | 4 | 1 | Controlled shutdown of the NPE TSW | None |  |  | M. Anna |  | 2014-01-23 |  |  | EX | 15 |  |  | Observed an ERROR in the log when none was expected. Not a failure of requirement. Needs further investigation. May be related to EGSE DR 3469.
| 2 | 5 | 1 | Emergency Shutdown Function | TSW_SIQT_Emergency_Shutdown.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
| 2 | 6 | 1 | Logging Behaviors | AAAA_MDU_Set_Config_Var_Utility.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | AAAA_MDU_Set_OpMode_Var_Utility.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Bad_Syntax.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_Telemetry.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30
| 2 | 7 | 1 | Script Aborts on Tlm Failure | TSW_SIQT_Measurement_Check_Failures.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Prompt_Operator_MITE.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
|  |  | 2 | Halts upon Measurement Check Failure | TSW_SIQT_Measurement_Check_Failures.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Prompt_Operator.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
| 2 | 8 | 1 | LM Interface | None |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30
|  |  | 2 | Testing the Heartbeat Request/Response & Monitor Msg | TSW_SIQT_EGSE_Interface.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30 |  |  | Agreed with LM CPE to rerun and collect all data for review to resolve. Witness disagreed with what was seen.
[5 empty] | TSW_SIQT_EGSE_Interface.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30
|  |  | 3 | TCC Abort Script Function | TSW_SIQT_EGSE_Interface.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30
|  |  | 4 | TTC/ATP Connectivity functions to TestEngineExecutive | TSW_SIQT_EGSE_Interface.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 30
[5 empty] | TSW_SIQT_Prompt_Operator.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Prompt_Operator.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Prompt_Operator.xts |  |  | M. Anna |  | 2014-01-23 |  |  | Pass | 5
7.1 | 3 | 1 | 1 | Power Supply Functions | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | STE_MDU_70V_AB_OFF_ON.xts |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 10
[5 empty] | TTCPSCNTRL.xts |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TTCPSCNTRL.xts |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
|  | 1 | 2 | Prime Power Outputs | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Prime_Power_Outputs.xts (OFF) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Prime_Power_Outputs.xts (ON) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
| 3 | 2 | 1 | Total RF Power | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | TSW_SIQT_STE_Total_RF_Power.xts |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 20
[5 empty] | TSW_SIQT_STE_Total_RF_Power.xts |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 20
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-23 |  |  | Pass | 5
|  |  | 2 | Lband Output Return Loss | TSW_MDU_Lband_Output_Return_Loss.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 5
| 3 | 3 | 1 | TKS Allen Deviation | TSW_SIQT_MDU_TKS_Allen_Deviation.xts |  |  | H. Yaniero |  | 2014-01-24 |  |  | Pass | 90
|  |  | 2 | MDU VCXO TKS Phase Noise | Utility_MDU_Power_OnOff.xts (OFF) |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 5
[5 empty] | Utility_MDU_ReInitialization.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_VCXO_TKS_Phase_Noise.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 35
|  |  | 3 | AFS Signals | Utility_MDU_AFS_Setup.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | Utility_MDU_AFS_Setup.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | Utility_MDU_AFS_Setup.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 15
[5 empty] | Utility_MDU_AFS_Setup.xts |  |  | W. Guan |  | 2014-01-23 |  |  | Pass | 15
|  |  | 4 | ECTS/EIE Verification | Utility_MDU_Power_OnOff.xts (OFF) |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | Utility_MDU_ReInitialization.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 15
[5 empty] | TSW_SIQT_SFM_NEC_Commanding.xts |  |  | M. Anna |  | 2014-01-24 |  |  | EX | 10 |  |  | Measurement failure due to timeout. Need to examine and re-run.
| 3 | 4 | 1 | Telemetry | Utility_MDU_Power_OnOff.xts (OFF) |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | Utility_MDU_ReInitialization.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_Telemetry |  |  | M. Anna |  | 2014-01-24 |  |  | EX | 30 |  |  | Needs data review. Could not find listed telemetry in report to verify.
|  |  | 2 | TLM verification through the EGSE Ethernet Interface | TSW_SIQT_TlmAnalog.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TlmDiscrete.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TlmSerial.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TlmAnalog.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TlmDiscrete.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
[5 empty] | TSW_SIQT_TlmSerial.xts |  |  | M. Anna |  | 2014-01-24 |  |  | Pass | 5
|  |  | 3 | MDU Test Bus (MUX Bus) | TSW_SIQT_MDU_Test_Bus.xts | [7 empty] | N/A | 120 |  |  | Test Case to be removed - In Reviewing the requirements with the SPE and Exelis SQA it was agreed that the requirements being coverd by this test case have incorrectly been allocated to TSW and the Test Case will be Removed from teh Test Procedure. (DR's IRS1363, SRS3451)
| 3 | 5 | 1 | HPE Timing Signal | MDU_HPE_Signals.xts |  |  | W. Guan |  | 2014-01-24 |  |  | Pass | 30
| 3 | 6 | 1 | Bus BDP Cmd Transaction | mdu_nds_bdp_commands.xts |  |  | W. Guan |  | 2014-01-24 |  |  | Pass | 10
|  |  | 2 | 1553 Black Bus | Utility_MDU_Reinitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Test_1553_Side.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Reinitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Test_1553_Side.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Reinitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Test_1553_Side.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Reinitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_Test_1553_Side.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Reinitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
|  |  | 3 | 1553 Inject All Telemetry | TSW_SIQT_1553_Inject_All_Telemetry.xts |  |  | W. Guan |  | 2014-01-24 |  |  | Pass | 40 |  |  | Data Review in process
|  |  | 4 | SV Attitude message functions | TSW_SIQT_Test_SV_Attitude_Msg.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 20
|  |  | 5 | NAV Messaging | for SWIT: Utility_Validate_Nav_Messages_Processing_for_SWIT_Start.xts for SIQT: Utility_Validate_Nav_Messages_Processing.xts |  |  | M. Hazel |  | 2014-01-24 |  |  | Pass | 300 180 |  |  | Verifications steps approved Pending Data Review and approval
7.1 | 4 | 1 | 1 | LBCR Nominal State | MITE/MAR: MDU_Configuration.xts NPEITE: NPE_Configuration.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 210 |  |  | Data Review in process
[5 empty] | Utility_RF_ASSY_Manual_Control.xts | [8 empty] | 5 |  |  | Not Required
|  |  | 2 | LBCR Self Test | MITE/MAR: TSW_SIQT_LBCR_Verification_with_TTX.xts NPEITE: TSW_SIQT_NPE_LBCR_Verification_with_TTX_with_C.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 30 |  |  | Data Review in process
|  |  | 3 | LBCR SVID Test | Utility_MDU_Reinitialization.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | Utility_RF_ASSY_Manual_Control.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | MDU_SVID.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Fail | 120 |  |  | Failed the final code present check when LBCR had OOM error. Need to re-examine chosen test method and determine if we can scale this test back.
|  |  | 4 | LBCR Lband signals' correlation loss Data Acquisition Test | MITE/MAR: Utility_MDU_Reinitialization.xts NPEITE: NPE_Configuration.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 15 |  |  | Data Review in process
[5 empty] | MITE/MAR: NPE_Correlation_Loss.xts NPEITE: TSW_SIQT_NPE_Correlation_Loss.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 5 |  |  | Data Review in process
| 4 | 2 | 1 | Lband In-Band Emissions | Utility_MDU_Power_OnOff.xts (OFF) |  |  | M. Hazel/ H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | M. Hazel/ H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_ReInitialization.xts |  |  | M. Hazel/ H. Yaniero |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_Lband_In-Band_Emissions.xts |  |  | M. Hazel/ H. Yaniero |  | 2014-01-25 |  |  | Pass | 130 |  |  | Started 1/25/2014 Collect all artifacts and convene with Validation team to review Sunday 1/26/2014
|  |  | 2 | Lband Phase Noise | Utility_MDU_ReInitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_Lband_Phase_Noise.xts |  |  | M. Hazel/ H. Yaniero |  | 2014-01-25 |  |  | Pass | 180
|  |  | 3 | Out-of-Band Emissions | Utility_MDU_ReInitialization.xts |  |  | N/A |  | N/A |  |  | N/A | 15 |  |  | Not Required
[5 empty] | MDU_Lband_OOBE.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 450 |  |  | Data Review in process
| 4 | 3 | 1 | Non Standard Code | MITE/MAR: Utility_MDU_Reinitialization.xts NPEITE: NPE_Configuration.xts |  |  | N/A |  | N/A |  |  | N/A | 15 |  |  | Not Required
[5 empty] | Utility_RF_ASSY_Manual_Control.xts |  |  | N/A |  | N/A |  |  | N/A | 5 |  |  | Not Required
[5 empty] | MITE/MAR: TSW_SIQT_MDU_Non_Standard_Codes.xts NPEITE: TSW_SIQT_NPE_Non_Standard_Codes.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 25 |  |  | Blackline to review requirement that was recently added to this test.
|  |  | 2 | Cross Link Transmit | MITE/MAR: Utility_MDU_Reinitialization.xts NPEITE: NPE_Configuration.xts |  |  | N/A |  | N/A |  |  | N/A | 15 |  |  | Not Required
[5 empty] | Utility_RF_ASSY_Manual_Control.xts |  |  | N/A |  | N/A |  |  | N/A | 5 |  |  | Not Required
[5 empty] | MITE/MAR: MDU_Crosslink_Transmit.xts NPEITE: TSW_SIQT_NPE_Crosslink_Transmit.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 10 |  |  | Data Review in process
|  |  | 3 | Cross Link Receive | MITE/MAR: Utility_MDU_Reinitialization.xts NPEITE: NPE_Configuration.xts |  |  | N/A |  | N/A |  |  | N/A | 15 |  |  | Not Required
[5 empty] | Utility_RF_ASSY_Manual_Control.xts |  |  | N/A |  | N/A |  |  | N/A | 5 |  |  | Not Required
[5 empty] | MITE/MAR: MDU_Crosslink_Receive.xts NPEITE: TSW_SIQT_NPE_Crosslink_Receive.xts |  |  | J. Fazio |  | 2014-01-24 |  |  | Pass | 10 |  |  | Data Review in process
|  |  | 4 | GED and LLED Interfaces | Utility_MDU_ReInitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_GED_LED_Events.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
|  |  | 5 | Transmitter Control | Utility_MDU_ReInitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | TSW_SIQT_MDU_Transmitter_Control_Word.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 75
|  |  | 6 | Code Dwell Imbalance | Utility_MDU_ReInitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | MDU_Code_Dwell_Imbalance.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 5
|  |  | 7 | MDU X1 Epoch Adjust | Utility_MDU_ReInitialization.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
[5 empty] | MDU_X1_Epoch_Adjust.xts |  |  | M. Hazel |  | 2014-01-25 |  |  | Pass | 15
|  |  | 8 | Key Supercession | A_npe_key_scheduling_scenarios_1_to_4.xts |  |  | J. Fazio |  | 2014-01-25 |  |  | Pass | 20 |  |  | Data Review in process
7.1 | 5 | 1 | 1 | MDU Hard Reset Bootstrap | Utility_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 1
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 1
[5 empty] | TSW_SIQT_Hard_Reset_Bootstrap.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 10
|  |  | 2 | Soft Reset the Boot Software | TSW_SIQT_Soft_Reset_Bootstrap.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 10
| 5 | 2 | 1 | Stored Command Status | Utility_MDU_Power_OnOff.xts (OFF) | [7 empty] | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) | [7 empty] | Pass | 5
[5 empty] | TSW_SIQT_Stored_Commands.xts | [7 empty] | Pass | 5
| 5 | 3 | 1 | Boot valid/Invalid Serial Command Status | BOOT_MDU_Power_OnOff.xts(OFF) |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | BOOT_MDU_Power_OnOff.xts(ON) |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Invalid_SMC.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 40 |  |  | DR 3488 -Dry Run test script TSW_SIQT_Invalid_SMC.xts has the wrong test name tag for SMC0320. The Test tag needs to change to reflect "Request_Command_Status(Nav)". The Audit team was able to identify that the test passed but was incorectly titled.
|  |  | 2 | CCAs and Stored Commands | BOOT_MDU_Power_OnOff.xts (OFF) |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | BOOT_MDU_Power_OnOff.xts (ON) |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | TSW_SIQT_CCAs_and_Stored_Commands.xts |  |  | H. Yaniero |  | 2014-01-25 |  |  | Pass | 10
|  |  | 3 | Valid Commands/Reserved SMCs | Utility_MDU_Power_OnOff.xts (OFF) |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Valid_Commands.xts |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Reserved_SMCs.xts |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 60
| 5 | 4 | 1 | Valid MUB | TSW_SIQT_Upload_Nominal_MUBs.xts |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 10
[5 empty] | Upload_Nominal_MUB.Time.xts |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 10
|  |  | 2 | Invalid MUB | TSW_SIQT_Invalid_Checksum.xts |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 10
|  |  | 3 | Too Large MUB | TSW_SIQT_Too_Large.xts |  |  | W. Guan |  | 2014-01-25 |  |  | Pass | 10
| 5 | 5 | 1 | Dump telemetry | Boot_MDU_Power_OnOff (OFF) |  |  | W. Guan/ M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Boot_MDU_Power_OnOff (ON) |  |  | W. Guan/ M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | TSW_SIQT_Telemetry_Dump |  |  | W. Guan/ M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (OFF) |  |  | W. Guan/ M. Hazel |  | 2014-01-25 |  |  | Pass | 5
[5 empty] | Utility_MDU_Power_OnOff.xts (ON) |  |  | W. Guan/ M. Hazel |  | 2014-01-25 |  |  | Pass | 5
7.1 | 6 |  |  | Analysis | [12 empty] | Analysis |  |  |  |  | In Process | Will be Completed Post SIQT
6 | 24 | 25 | 92 | Test Execution(Does not include Analysis) | 183 | 203 | 203 |  |  | 184 |  |  | 182 | 3691 |  | 0
Test Cases | Test Sub Cases | Test Sect. | Test Groups |  | 20 | [16 empty] | Task Status Legend:
Needs examination
[5 empty] | ExecutionStatus legend: | [10 empty] | #DIV/0! | [5 empty] | Work identified and in progress
[5 empty] | Pass = Passed execution and verification. | [7 empty] | 182 | [8 empty] | Reviewed, Ready for Test
[5 empty] | EX = Unable to execute due to procedure or script issue. Cannot determine verification. | [7 empty] | 8
Fail = Failed verification.
[5 empty] | SWIT Run Status |  | Total Script Executions Planned | Total Script Executions | % Scripts Run | Total Test Case | Passed | Test Case Passed | Test Case Failed | Test Case Execution Issue |  |  | Test Case N/A
[5 empty] | Total Test Scripts |  | 183 | 203 | 99.51% | 203 | 0 | 182 | 1 | 8 |  |  | 11
[5 empty] | Scripts Executed |  | 203 | 202
[5 empty] | Not Including Analysis |  | 6
[5 empty] | TestCases |  | 25 | 6
[5 empty] | Total Test Subcases |  | 92 | 24
[5 empty] | Total Sections |  |  | 25
[5 empty] | Test Case |  | TSW Test Case | Subcase | Scripts | TC | Total Pass | EX | Pass | Failed | Execution Issue
[5 empty] | 7.1.1.1 |  | 1 | 1 | 10 |  | 9 | 1 | 8 | 0 | 1
[5 empty] | 7.1.1.2 |  | 2 | 1 | 15 |  | 15 | 4 | 11 | 0 | 4
[7 empty] | 2 | 2 | 9 |  | 9 | 0 | 9 | 0 | 0
[7 empty] | 2 | 3 | 27 |  | 27 | 0 | 27 | 0 | 0
[7 empty] | 2 | 4 | 1 |  | 1 | 1 | 0 | 0 | 1
[7 empty] | 2 | 5 | 1 |  | 1 | 0 | 1 | 0 | 0
[7 empty] | 2 | 6 | 9 |  | 9 | 0 | 9 | 0 | 0
[7 empty] | 2 | 7 | 4 |  | 4 | 0 | 4 | 0 | 0
[7 empty] | 2 | 8 | 8 |  | 8 | 0 | 8 | 0 | 0
[5 empty] | 7.1.1.3 |  | 3 | 1 | 10 |  | 10 | 0 | 10 | 0 | 0
[7 empty] | 3 | 2 | 9 |  | 9 | 0 | 9 | 0 | 0
[7 empty] | 3 | 3 | 13 |  | 13 | 1 | 12 | 0 | 1
[7 empty] | 3 | 4 | 11 |  | 10 | 1 | 9 | 0 | 1
[7 empty] | 3 | 5 | 1 |  | 1 | 0 | 1 | 0 | 0
[7 empty] | 3 | 6 | 13 |  | 13 | 0 | 13 | 0 | 0
[5 empty] | 7.1.1.4 |  | 4 | 1 | 7 |  | 5 | 0 | 5 | 1 | 0
[7 empty] | 4 | 2 | 8 |  | 7 | 0 | 7 | 0 | 0
[7 empty] | 4 | 3 | 17 |  | 11 | 0 | 11 | 0 | 0
[5 empty] | 7.1.1.5 |  | 5 | 1 | 4 |  | 4 | 0 | 4 | 0 | 0
[7 empty] | 5 | 2 | 3 |  | 3 | 0 | 3 | 0 | 0
[7 empty] | 5 | 3 | 10 |  | 10 | 0 | 10 | 0 | 0
[7 empty] | 5 | 4 | 4 |  | 4 | 0 | 4 | 0 | 0
[7 empty] | 5 | 5 | 5 |  | 5 | 0 | 5 | 0 | 0
[5 empty] | 7.1.1.6 |  | 6 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0
[9 empty] | 199 |  | 188 | 8 | 180 | 1 | 8 |  |  | Sanity Check

## SW Action Registry
Action Item # | Test Case Number | Summary | Description | Planned to Close | Open Date | Due Date | Closure d | Closed Date
1 | 7.1.2.2.3 7.1.2.2.4 | Entry of Calibration Dates | During execution of test cases (7.1.2.2.3,7.1.2.2.4) it was noticed that the equipment calibration dates were all set to the current date. It was determined that this was caused by the method used to install the software for SIQT(Clean Install) | Need to determine where, in the STE build out process or out of process, the entry of calibration needs to be accomplished after a clean install, redline the appropriate document(s) and enter the calibration data for this event. | 2014-01-22 | Must be Closed before close of SIQT
2 | 7.1.2.8.2 | Pass/Fail Shown in TCC Window? | After this test was run there was inconsistent recall amongst the witnesses as to whether the pass fail was shown in the TCC Window. A screen capture was done for the fail case but not for the pass case. The test case was passed but it was agreed to rerun the test case. | Rerun the test case and collect a complete set of artifacts. The artifacts will then be reviewed to determine if a DR is needed. | 2014-01-23 | Must be Closed before close of SIQT
3 | 7.1.3..3.1 | Too Many Discrepancies between Script Prompts and test procedure | The script prompts do not correlate with the test procedure . It was not possible to redline during the test | Create the redline off line and then rerun the test when ready. | 2014-01-23 | Must be Closed before close of SIQT | Updated Test Case was written and inserted into the Master Redline Test Procedure book. The Test case was run and redlined to procide a final redline version procedure | 2014-01-24
4 |  | TIC Setup / STE HW Setup | Contact the HW team responsible for the STE and inform them that there was a failure to properly configure the TIC. We have seen this issue numerous times in the past and perhaps the HW team needs to update their STE recovery procedure. (The unplanned power loss on the Saturday before the start of SIQT Dry Run is most likely responsible for putting the TIC in a bad state.) | Contact Vince C to discuss. | 2014-01-26 | Must be Closed before close of SIQT
5 | 7.1.5.5.1 | Red -88 needs followup SRS 3585 | Removal of two requirements from a specific test. These requirements are spread throughout the test case in a similar manner and we should discuss with LM CPE. | Talk to Dave C. | 2014-01-28
6 | 7.1.5.5.1 | Red -88 needs followup IRS 1372 | Removal of two requirements from a specific test. These requirements are spread throughout the test case in a similar manner and we should discuss with LM CPE. | Talk to Dave C. | 2014-01-28
7 | 7.1.4.1.1 | Blue Line Requirement Issue | "This test eval does not verify local disk storage space." Need to examine. |  | 2014-01-28
8 | 7.1.4.3.1 | Black Line Requirement Issue | -218 A requirement was added just before the start of SIQT Dry Run into this section and may not apply. (SRS 4361) Email discussion occurred where Howard B. stated this should be verified in the continuous monitor tests. |  | 2014-01-28
9 | 7.1.4.3.3 | Black Line Requirement Issue | -220 There is a verify statement that does not have an associated requirement. The test operator and witnesses were not about to find any evidence in the results to pass this test eval. We may test this timing requirement elsewhere and be able to remove this Test Eval step.
10 | 7.1.4.3.3 | Blue Line Requirement Issue | Line 1068 ("nibble") is a Test Eval with no requirement. The test eval is also written poorly. The operator and witnesses had great trouble understanding. "Verify the Cross Link Receive data in the EIE_Xlink_Receive_Input.xml file is sent in a two bit format."
7.1.4.3.3

## Remaining Tests
[6 empty] | Description | Actions Taken
1.1.6 | Record and confirm test directory (root) is established for SIQT. | None |  |  |  | Procedure issues, require re-write or removal. These steps may take place during installation. | Sub Case Deleted. Action Closed.
2.1.5 | Prompt Operator from ITE STE | TSW_SIQT_Prompt_Operator.xts |  |  | EX | DR3471 Need to rewrite verify for this test and re-test. | 1/27 K. Adam - Re-writing test case. 1/27 M. Anna retest failed, need to discuss.
2.1.6 | Detection of Faults at Startup | None |  |  | EX | Need to verify if this Test Eval should be a 48 or a 0. There was confusion regardig this test eval. The 48 was part of a referenced piece of log file and does not effect the test. Need to re-write verify to make more clear and rerun. No data saved. | 1/27 Re-wrote test case. Re-ran, passed. Ready for Re-run. 2/10 Verification re-written. Need written explanation to present to Exelis SQA, LM and Aerospace and get their sign-off of pass.
2.1.9 | AR Instrument Power Down detected by ITE | TSW_SIQT_Self_Test.xts | M. Anna | 2014-01-22 | EX | Needs further verification of non-matching numbers. | 1/28 W. Guan to examine.
2.1.12 | Detect Invalid Configuration With Missing Configuration File | None | M. Anna | 2014-01-22 | EX | Needs data review to verify results. | 1/28 W. Guan to examine.
2.4.1 | Controlled shutdown of the NPE TSW | None | M. Anna | 2014-01-23 | EX | Observed an ERROR in the log when none was expected. Not a failure of requirement. Needs further investigation. May be related to EGSE DR 3469. | 1/27 Re-ran and passed. Need to examine previous error and then re-run for score.
2.8.2 | Testing the Heartbeat Request/Response & Monitor Msg | TSW_SIQT_EGSE_Interface.xts | M. Anna | 2014-01-23 | Pass | Agreed with LM CPE to rerun and collect all data for review to resolve. Witness disagreed with what was seen. | 1/27 M. Anna reran, had issues, Need to investigate. 1/28 Re-written, Hamida to execute for score on 1/29
3.3.4 | ECTS/EIE Verification | TSW_SIQT_SFM_NEC_Commanding.xts | M. Anna | 2014-01-24 | EX | Measurement failure due to timeout. Need to examine and re-run. | Possible EIE ERROR. Need assistance with this… HY 1/28/14 1/28 Roger tasked to examine.
3.4.1 | Telemetry | TSW_SIQT_MDU_Telemetry | M. Anna | 2014-01-24 | EX | Needs data review. Could not find listed telemetry in report to verify. | 1/28 W. Guan to examine. 2/10 Verification re-written. Need written explanation to present to Exelis SQA, LM and Aerospace and get their sign-off of pass.
3.4.3 | MDU Test Bus (MUX Bus) | TSW_SIQT_MDU_Test_Bus.xts |  |  |  | Test Case to be removed - In Reviewing the requirements with the SPE and Exelis SQA it was agreed that the requirements being coverd by this test case have incorrectly been allocated to TSW and the Test Case will be Removed from teh Test Procedure. (DR's IRS1363, SRS3451) | 1/28 Confirmed with Trish that removed section's requirements are covered elsewhere. Section removed. N/A.
3.6.3 | 1553 Inject All Telemetry | TSW_SIQT_1553_Inject_All_Telemetry.xts | W. Guan | 2014-01-24 | Pass |  | Data Review in process 1/31 Test did not pass, needs re-run.
4.1.3 | LBCR SVID Test | MDU_SVID.xts | H. Yaniero | 2014-01-25 | Fail | Failed the final code present check when LBCR had OOM error. Need to re-examine chosen test method and determine if we can scale this test back. | LBCR Failure Joe Barcelo is looking into this… 1/27/2014 HY
4.3.7 | MDU X1 Epoch Adjust | MDU_X1_Epoch_Adjust.xts | M. Hazel | 2014-01-25 | Pass | 1/25 Script did not run. DR3486. 1/26 Fixed script issues, STE not in good state. Needed to run reinit. Script run to completion but had measurement failure. Needs investigation. | Equipment needed to be set manually. EquipmentList.xml had the wrong Port addess (Port 3) when it should be port 6. port 3 was being used by another instrument (Power meter) which cause the different errors during the test. 1/27/14 HY 1/28 HY re-run for score with witnesses. 1/28 Run for score PASSED.
5.2.1 | Stored Command Status | TSW_SIQT_Stored_Commands.xts |  |  | Pass | DR 3487 - TSW Dry Run SIQT Store Command Script missing stored commands - During TSW Dry run SIQT event the team identified the test data report showed that the script issued the wrong command as identified by the test measurement name.The Procedure will need to be reviewed to ensure it matches the script updates required. Marked fail as it did not validate all Stored CMDS | Updated script as per the 801 Stored Command section. Updated procedure to verify correct values as per the 801. 1/27/14 HY 1/27 M. Anna reran, script passed but incorrect results. Need to examine. 1/28 Missing one more command (31). Edited script and HY re-run for score with witnesses. 1/28 Run for score PASSED.
5.4.3 | Too Large MUB | TSW_SIQT_Too_Large.xts | W. Guan | 2014-01-25 | Pass | TSW SIQT TC 7.1.5.5.3 Too Large MUB Failed Script does not verify requirement Correctly TSW_SIQT_Too_Large.xts script does not properly evaluate teh requirements assigned to the TSW SIQT TC 7.1.5.4.3 Too Large script. The TSW SIQT test procedure will require updates to mathc the corrected script. The TLM respones was an updload overflow while the test procedure was looking for an timeout error. | SRS_1772 The NPE TSW shall stop the current test and indicate test failure if the NPE TSW does not receive Upload Block telemetry messages within the amount of time specified by the Test Scripts. REMOVE this line: Verify that the test stops and indicates upload failure due to time out This Verification is checked above not sure why this is checked again. 7.1.5.4.1 1/28/14 HY 1/28 HY re-run for score with witnesses. 1/28 Run for score PASSED.

## Sheet1
TSW Test case | Sub case | Count of Run Status P/F
1 |  | 1
| 1 | 1
2 |  | 8
| 1 | 1
| 2 | 1
| 3 | 1
| 4 | 1
| 5 | 1
| 6 | 1
| 7 | 1
| 8 | 1
3 |  | 6
| 1 | 1
| 2 | 1
| 3 | 1
| 4 | 1
| 5 | 1
| 6 | 1
4 |  | 3
| 1 | 1
| 2 | 1
| 3 | 1
5 |  | 5
| 1 | 1
| 2 | 1
| 3 | 1
| 4 | 1
| 5 | 1
6
(empty) |  | 178
| (empty) | 178
1
| 1 | 1
Total Result |  | 202