## TSW_SIQT_Dry_Run_1-21_2014
This spread sheet is the report on the data review comments related to the GPSIII NPE TSW SIQT Dry Run performed during the weeks of Jan 22, 2014 to Jan 30, 2014
| Note 1: | Reviewer's Rating given here is based on the test procedure being executed, not tied to the requirements being met at all.
| Note 2: | Reviewer's Rating given here is an independent rating, regardless of the redline/blackline issued during the tests.
| Note 3: | Reviewer's Rating given here is an independent rating, weighted on the data captured,logged during the tests. Some of the tests this reviewer did not witness.
| Note 4: | LM team will review TC02, and TC05 test data.
| Note 5: | Light Brown colored on the Item column indicated tests done in SAP lab with the NPEITE, all other tests were in the SW lab with MITE/MAR 1
Item | Test Case | Subcase | section | Section Titlte/Proposed Object Text | Review document Name | Reviewer Comment | Reviewer Rating on this section | Rating rationale
1 | 1 | 1 | 1 | Initial Setup | N/A | This section produced no data file. This reviewer witnessed the test on 1-21-14, and on step 15, DR 3467 was written against the test procedure due to the installation fialed to start the engine as the WATLOW did not start. WATLOW is a thermal controller | fail | DR was issued
2 | 1 | 1 | 2 | Confirm TSW Desktop Shortcuts | N/A | This section produced no data file. This reviewer witnessed the test on 1-21-14, and on step 24, it failed to have the util TLM_Dashboard.exe (a Cat4 tool) being installed into the appropriate folder. Hence, it failed on creating the short cut for it. This tool is needed for check out the 1553 box. | fail | Failed to be a clean execution
3 | 1 | 1 | 2 | Confirm TSW Desktop Shortcuts | N/A | The second issue for this short cut failure in step 24 was that this TLM_Dashboard.exe was not packaged into the Util SIRN in the clearcase. Need SCM to bring in the official released SIRN items. It was declared as not staged correctly. | fail | Failed at the installation step.
4 | 1 | 1 | 3 | Confirm SQL Server Management Studio is available on PC: | N/A | This section produced no data file. This reviewer witnessed the test on 1-21-14. All steps under this section were fine. | pass
5 | 1 | 1 | 4 | Power On and Configuration Verification | Only 1 screen shot file of 2 pages was saved for this run | Page 1 of the screen shot showed the SQL Querry12.sql, and page 2 has SQLQerry13.sql_MITE_CTR_1. The data base querry looked fine. | pass
6 | 1 | 1 | 5 | Record SIRN ID for the TSW being used for TSW SIQT. | ScriptResults_8.xls, XTSHistory, ITT_Debugging_ITE.log, ITT_Debugging_MAR.log | No error, no warning, no incomplete found in any of these files | pass
7 | 1 | 1 | 6 | Record and Confirm Test Directory (root) established for SIQT. | N/A | This section prodcued no data file for review. | pass
8 | 1 | 1 | 7 | Configure MDU and STE to a "Nominal" operational state. | ScriptResults_9.xls, XTSHistory, ITT_Debugging_ITE.log, ITT_Debugging_MAR.log, ScriptResults_10.xls, | The two script result files, ITT_Debugg_ITE.log and the XTSHistory were okay. Lines 9350-9356 in the file ITT_Debugging_MAR.log showed an INFO message that : ITT_Specific MDU 1553_MDU Normal TLM Bus Transaction Failure, status = DataNoResponse Error. Another message on line 10015: INFO ITT::SSD::Test Equipment::DI.USB DioBase::WriteChannel = Data = False | fail | Bus failure indicated in the log file signified a non-clean run.
9 | 1 | 1 | 8 | Optional: Used during testing to do a Soft Reset to the MDU. | N/A | This section was not executed during this dry run | N/A
10 | 1 | 1 | 9 | Optional: Use for Restoring STE to a Nominal Test Execution Working State | SID1_2 folder/ATP_Schema fail_bit_map file | The bit map image showed failure in starting the test twice. Failure due to "Could not find the file" SID1 and SID2 ScriptResult files showed no start time, and no end time. | fail | Test could not even start.
11 | 1 | 1 | 9 | Optional: Use for Restoring STE to a Nominal Test Execution Working State | SID3_4 folder/ScriptResults, XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | The scriptResult file showed no error, no unfinished. XTSHistory ok as well. The ITT_Debugging_ITE file line 3199 reported a failure in Execute Script Profile with unknown profile step "Script" ignored. The AR log line 3582 has a an INFO message that : ITT_Specific MDU 1553_MDU Normal TLM Bus Transaction Failure, and line 3862 has : INFO ITT::SSD::Test Equipment::DIO=USB DioBase::WriteChannel = Data = False | fail | Failed to be a clean execution
12 | 1 | 1 | 9 | Optional: Use for Restoring STE to a Nominal Test Execution Working State | SID5 folder | This folder showed Engine Connection Failure | fail | Test could not even start.
13 | 1 | 1 | 9 | Optional: Use for Restoring STE to a Nominal Test Execution Working State | SID6_7 folder/scriptResults, XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | The scriptResult file showed no error, no unfinished. XTSHistory ok as well. For SID 7, The ITT_Debugging_ITE file line 8306 reported a failure in Execute Script Profile with unknown profile step "Script" ignored. The MAR log line 7698 has a an INFO message that : ITT_Specific MDU 1553_MDU Normal TLM Bus Transaction Failure, and line 3862 has : INFO ITT::SSD::Test Equipment::DIO=USB DioBase::WriteChannel = Data = False. Line 8352 showed a message for RESET_EIE_REQUEST (EIE command flash called). | fail | Failed to be a clean execution, and need some clarification to these INFO messages on the two log files.
14 | 3 | 1 | 1 | Power Supply Functions | SID76…82 folder/scriptResults, XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | The scriptResult file showed no error, no unfinished. XTSHistory, ITT_Debugging_ITE files were good. ITT_Debugging_MAR log line 5245 indicated a MDU Normal TLM Bus transcation failure. And line 5792 showed Test Equipment DIO=USB DioBase= write channel = Data = False. | fail | Failed to be a clean execution, and need some clarification to these INFO messages on the MAR log file.
15 | 3 | 1 | 2 | Prime Power Outputs | SID87_91 folder/scriptResults, XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | All these files were reviewed, and found no error, no issue, no exception. | pass
16 | 3 | 2 | 1 | Total RF Power | SID83_86 folder/scriptResults, XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | All these files were reviewed, and found no error, no issue, no exception. | pass
17 | 4 | 3 | 8 | Key Scheduler | SID 2982 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | In ScriptResults file : Lines 597 and 697 expected 0 to pass, raw result = -4. Fail less than than low limit. All other files had no error, no exception, no issue. | pass | It was a negative test, to ensure the failure will be reported.
18 | 4 | 3 | 2 | Xlink Transmit | SID 2977 and 2978 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | ScriptResults file: line 919 LBCR NDS Transmission Dectect raw =0, spec > 0. XTSHistory file line 6349 to have a GUI message of wait an additional 22 seconds to let the TLM Analysis Finish. But on line 6350 indicated to wait <21000 ms>, and line 6114 | pass? | Does this raw value matter to the test? If so, could not pass this test. Also, the wait time, which one is correct?
19 | 4 | 3 | 2 | Xlink Transmit | SID 2977 and 2978 an input file = EIE_NDS_DATA_IDD_Hopping xml document and and output file = EIE Slot 6 rpe3sp5f file | These two files are used to verify that the transmitted data matched to the script file for the data transmitted from the MDU to the EIE with IDD bypass disabled. This reviewer confirmed that the input file matched with the output file for all 65 hops. | pass | Good match on the data being tramsmitted.
20 | 4 | 3 | 2 | Xlink Transmit | SID 2977 and 2978 ITT_Debugging_AR log | The _AR file line 4346 has an error: Data Storage DBComm - The insert statement conflicted with the FOREIGN KEY constraint…. This error had many occurances in the file. | Need clarification | Does this error matter to the result of the test?
21 | 4 | 3 | 2 | Xlink Transmit | SID 2977 and 2978 ITT_Debugging_ITE log | The log file line 2087 has a warning: LBCR Process NAV Message, NDS number incorrect (5), expected (0). Also, from lines 2175 to 2382 there were 208 mismatches from INFO: Safe Test Instrument LBCR compare Nav Message() mismatches at offset 144, 148, 154... | Need clarification, who set the high limit on the mismatch value being 250? | A total of 208 mismatches, as the test had set the limit to 250, the test was considered pass. Had the limit be lower, this test would have failed.
22 | 4 | 2 | 3 | Out-of-Band Emissions | SID 2963 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | In ScriptResults file : lines 385, 427, 469, 511… Each of the sweep test, raw value received =0, spec <0, why the result file considered them passed? All other data files looked fine, without error, warning, exception | fail | Failed to meet the spec.
23 | 4 | 3 | 1 | Non Standard Code | SID 2979 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | In ScriptResults file : lines 1494 to 1522 this section is to command MDU to send all std code and verify. However, on line 1509 Non-std code status didn't see the code present. On line 1648 it was to set LBCR to correlate on std code. Did not see if the test was executed. No measurement, no message to confirm the test started. | Need clarification | Don't know how the non-std code status could be verified.
24 | 4 | 3 | 3 | Cross Link Receive | ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log. Also in the LBCR loss folder/controller, DAQ1, and DAQ2 | In ScriptResults file : lines 836 LBCR NDS transmit Detect, raw =0, spec >0. Line 863 NDS message copmare result 0 = no mismatches, raw value =6, is that allowed? XTSHistory file line 9172 Issue output destination = GUI NDS_Message_Comparison_Result_High_limit set to 100 for TSW SIQT use due to the 8Hz Issue on OFU_B. Will this high limit affect the validity of the test? In ITT_Debugging_ITE file, line 4568 has a warning: LBCR Process NAV message number incorrect (264) expected (0). Should that be an indication of failure of the test? | fail | mismatches for the NDS messages made this test passing score questionable.
25 | 4 | 1 | 4 | LBCR L-Band signals' correlation loss Data Acquisition Test | SID 2975 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | In the SrciptResults file, show the code power corr loss loop: 0 of 1 only. | Need clarification: Is there a second loop to measure the correlation loss for each of the signals?
26 | 4 | 1 | 2 | LBCRVerification - TTX | SID 2974 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | In ScriptResults file : line 157 and 160 LBCR Tx start status (0=pass) raw=-4, spec =0. Line 1805 Verify L1CA Nav msg is equal to all 1's or all 0's raw =0, spec >0. Same on lines 1814 and 1823. In the XSTHistory file line 3172 INFO: measurement -FAIL. less than low limit. line 3331 FAIL greater than high limit | fail | Failed from matching the expected values on these signal, and exceeded the allowed limits.
27 | 4 | 1 | 1 | STE and LBCR set up | SIDs 2947 to 2959 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | Failures occured at various points of the set up caused this test to have so many SIDs. There were operator aborts, adding manual monitor , and inserting recovery test scripts still failed. In SID 2947 Utility Setup Test line 146 of the ScriptResult showed a raw value of -4, pass is =0. | fail | Too many trials and not clean run test.
28 | 4 | 1 |  | Staging | SIDs 2940 to 2946 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log | SIDs 2940 to 2943 had no start time, and no end time, which indicated they failed to start the test. SID 2944 had a failure due to TLM flow stopped and a message on Selected_secret_1553B_Primary Bus FAIL. 2946 had a selcted_secrte_1553B_Primary Bus_Scret greater than 1, expected =0 | fail | With so many failure reported in the result file, did not seem like a clean run
29 | 4 | 1 | 3 | LBCR SVID Test | SIDs 201-203 ScriptResults,XTSHistory, ITT_Debugginf_ITE.log, ITT_Debugging_AR log , Controller | In the controller file, line 342 has a warning LBCR Rx start Succeeded, but with Errors. The same warning occurred in line 327, 530, 636, 667, 723, 868. Also lines 652, 708, 841, 855 had warning LBCR Rx start - unable to start DAQ, FEP2 slices. Line 622 had a system service model - fault exception. Did not receive serial Z count (Fault details is equal to an exception detail likely created by Include Exception Details in Faults, whose value is "Did not receive serial Z count". at LBCR component.DAQ.NallatchCard Initialize Z count and Epoch 1). | fail | With so many failure reported in the controller file, did not seem like a clean run
30 | 4 | 2 | 1 | Lband In-Band Emissions | SID 197 XTSHistory file | In this file, line 3249 restore spec Analyszer did not get started. | Pass | Most likely this script should not be in this test, and was started by error from the test engine.

## Sheet2
Item # | Response
1 | DR 3467 Still being adressed - "In Work"
2 | TLM Dashboard in C:\Documents and Settings\All Users\Application Data\ITT\GPSIII\Utility\TLM_Dashboard currently exists, and can create shortcut. Does installer coyp file from ClearCase Dir …\Mite\07_Integration_Testing\Files\GPSIII CAT4 Tools\TLM Dashboard and create directory ?
3 | Need to confirm that Clearcase SIRN copy of Dashboard installs correctly and in proper location.
4 | SQL Server Management Studio is installed on PC:
8 | Issue occurred while MDU was in shutdown state. This is a normal event when MDU_Power_OnOFF is running and occurs when ran.
10 | XTSschema.xsd was not loaded from clearcase directory 07_Integration_Testing\Schemas into the Scripts directory at software load. File now exists. Need to check install procedure and see if it's getting loaded.
11 | "unknown profile Step "Script" issue is normal occurance during test run. Other issue, Issue occurred while MDU was in shutdown state. This is a normal event when MDU_Power_OnOFF is running and occurs when ran.
12 | ITE/AR connection Failure Action DR3469 underway.
13 | "unknown profile Step "Script" issue is normal occurance during test run. Other issue, Issue occurred while MDU was in shutdown state. This is a normal event when MDU_Power_OnOFF is running and occurs when ran.
14 | "unknown profile Step "Script" issue is normal occurance during test run. Other issue, Issue occurred while MDU was in shutdown state. This is a normal event when MDU_Power_OnOFF is running and occurs when ran.
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30