## Sheet1
Open IT Requests within Structures COE
2010-09-23
Item | Name | Remedy Ticket | Work Order # | Issue Description | Original Request Date | Status |  |  | Priorities Set on 10/5
1 | Cama, Dave | 867457 | WO# 309737 | B101 - IM Replace SSDROCW78W9994 with new Engineering Workstation - from Track-IT WO 309737 | 2009-10-14 | Delivered, setup and Remedy Closed. Minor issue with Clarity being worked on. Will check with dave Monday 11\9 | Create Remidy Ticket | power supply ordered | 1
2 | Johnson, Clayt | 831934 |  | Space Ball needs to be fixed | ~Two months ago | software reinstalled for spacemouse, monitor cable re-attached. It was loose. | Talk to Clayt | need to discuss within IT | 6
3 | Rappenecker, Kevin | 878948 |  | B101 F2 #224 - Unclass PC is very slow and is rebooting periodically on its own | 2010-09-22 | Old system picked up and new system delivered after security had authorized delivery | P/U Jerry Coccia RTD.. |  | 3
4 | Reese, Robert |  | 325459 (Work Order) | My laptop was never finished reimaging properly. It still goes blank without the AC adapter. | 2010-04-10 |  | check with database re-office ver… | order new battery | 5
5 | Reese, Robert |  | 322409 (Work Order) | I had a request in to add a second monitor. When Kevin Young was impacted in March, we dispositioned his monitors to myself and Joe. My monitor was replaced, but the original taken away. Mark promised to put in place but… | 2010-03-01 | 2nd lcd in closet, need to coordinate whe Rob. | check with database re-office ver…2007
6 | Reese, Robert | Not Submitted Yet | Not Submitted Yet | Our walkups in the trailer are in a state of disarray. Some are missing and the space has become a computer lab. I have not put in a WO, but can. |  | walkup pc's picked up per wo from space planning | walkups being recoverd per space planning request
7 | Landl, Dale | 854724 | 854724 | Reallocation of M.Godard’s 64bit workstation to replace my laptop. I don’t think anything has been done after Roxi submitted the requests. | 2010-08-20 | Completed Laptop picked up and replaced by Desktop pc. (profile backed up and restored) (minor issue with email needs to be resolved.) (Ntuser.dat) | assigned, look at Monday |  | 4 10/5/10
8 | White, Eric |  |  | UTAH (plotter at entrance to SCIF) isn't working. | 9/20/10 or 9/21/10 | Contacting Dan Rook for project to have power drop installed and printer located in appropriate area | waiting for RSO to created drop
9 | Giordano, Nathan | 804442 |  | Space mouse either doesn’t work, or works only with UG | Few months ago | Checking with marcia re-correct drivers for nastran | follow up with Nate Monday |  | 6
10 | Slusarczyk, Roxanne | No official request submitted - verbal request. | No official request submitted - verbal request. | Walk up office next to Nate Giordano has Nate’s old pc hooked to it from when data was transferred to new pc. EWI to start in that office 10/4/10; | email to Mark Hazel 9/20 indicating the office has to be ready by 10/1/10. | Incomplete. Mark needs to clean it up for the EWI | Pick up old PC MONDAY
11 | Slusarczyk, Roxanne | 863008 |  | Class computer VELA not working | Submitted 9/2/10 | Class pc being delivered to replace VELA | Re-image or replace VELA Monday |  | 7
12 | Slusarczyk, Roxanne |  |  | Structures Walk up area is unusable in Upper G Dock—not sure all pc’s have ever been set up but with all the computers sitting there it’s impossible to use |  | walkup pc's in place, generating class pc per discussion wth shireen for walkup area. Replacing Vela …see above | Repair or Replace walkup | get class machine back and on network | 8
13 | Slusarczyk, Roxanne | No official request submitted - verbal request. | No official request submitted - verbal request. | Unclass computer in my office area is not working | Email to Mark 9/20 | Checked walkup, it is slow but running. Checking inventory for flowdown upgrade. Not high priority | Repaor or Reimage Walkup |  | 9
14 | Alampi, Nick | Need to look up | Need to look up | Supposed to have his computer replaced with a new PC. | Over 1 year | System on bench being imaged, has motherboard issue. Working with Dell. |  |  | 2
15 | Alampi, Nick | Need to look up | Need to look up | PC issues with 8 computers out on the floor . | 2010-09-08 | Originally when I put the request in, IT replied back to me saying that they do not have any flow down computers available and closed my WO request. Then I called up x7000 again and talked to Cliff and he said to just send him the list of PC’s (which I did in the email below) and he would look into seeing what needs to be done w/ the computers, whether it’s cleaning them up, upgrading their memory, etc… | Flow down pc's being retrieved from floor. Contingent upon release from desktop (old user profiles released from supervision, I'll reimage and re-deploy) |  | 10
16 | Kuipers, Vicki | 843661 |  | Replace old 21# CRT monitor for new 22# LCD monitor | 2010-08-09 | The monitor has been at B101 for two months and has not been installed
17 | Kuipers, Vicki | No official request submitted - verbal request. | No official request submitted - verbal request. | When using headphones (for training, etc.), the sound still comes through the PC | 2010-07-14 | local speaker dicsonnected. Working with video issue with vicky. |  |  | 11
18 | Bill Trybulski | 835732 |  | Multiple log in dialog boxes when using the intranet (from the home page) | Late July | reinstalled IE8, no callback from bill. |  |  | 12
19 |  | 834735 |  |  |  | open new ticket july 7th. Has never worked for shireen | see Shireen - about this Monday;
20 | [5 empty] | 12 minutes to login to use ms outlook | known ost file - corrupted - delet ost file.