## Sheet1
Open IT Requests within Structures COE
2010-09-23
Item | Name | Remedy Ticket | Work Order # | Issue Description | Original Request Date | Status
1 | Cama, Dave | 867457 | WO# 309737 | B101 - IM Replace SSDROCW78W9994 with new Engineering Workstation - from Track-IT WO 309737 | 2009-10-14 | Incomplete 1/20/2010 Time, Logged by: Withers, Terrill A - Replace SSDROCW78W9994 - Image & Deploy Shipping to B101, Shipping Ticket 14428, system on cart, slated for delivery. This system needs to be imaged and delivered. | Create Remidy Ticket
2 | Johnson, Clayt | 831934 |  | Space Ball needs to be fixed | ~Two months ago | Incomplete. There are many issues with the SpaceMouse. They may be applications related. The "champion" for this device is no long with ITT. | Talk to Clayt
3 | Rappenecker, Kevin | 878948 |  | B101 F2 #224 - Unclass PC is very slow and is rebooting periodically on its own | 2010-09-22 | Hank is aware. Mark Hazel is investigating. Many systems are being reported as "slow". There is a general investigation on this issue currently underway. | Picked up pc per security request. Dan Gallis.
4 | Reese, Robert |  | 325459 (Work Order) | My laptop was never finished reimaging properly. It still goes blank without the AC adapter. | 2010-04-10 | Incomplete. Shireen wil ask Rob to provide list and Hank will talk with Mark. Had 2003. Mark upgraded to 2007. | check with database re-office ver…
5 | Reese, Robert |  | 322409 (Work Order) | I had a request in to add a second monitor. When Kevin Young was impacted in March, we dispositioned his monitors to myself and Joe. My monitor was replaced, but the original taken away. Mark promised to put in place but… | 2010-03-01 | Incomplete | check with database re-office ver…2007
6 | Reese, Robert | Not Submitted Yet | Not Submitted Yet | Our walkups in the trailer are in a state of disarray. Some are missing and the space has become a computer lab. I have not put in a WO, but can. |  | 1st floor also has an area - see #12 | walkups being recoverd per space planning request
7 | Landl, Dale | 854724 | 854724 | Reallocation of M.Godard’s 64bit workstation to replace my laptop. I don’t think anything has been done after Roxi submitted the requests. | 2010-08-20 | No communications since 8/24 | assigned, look at Monday
8 | White, Eric |  |  | UTAH (plotter at entrance to SCIF) isn't working. | 9/20/10 or 9/21/10 | Can't find any Remedy ticket for this. There is a Track-IT Work Order #325100 submitted by Jason Kostyshak for issues with UTAH. It was closed on 7/21/10 with the plotter working. | waiting for RSO to created drop
9 | Giordano, Nathan | 804442 |  | Space mouse either doesn’t work, or works only with UG | Few months ago | Incomplete. Mark | follow up with Nate Monday
10 | Slusarczyk, Roxanne | No official request submitted - verbal request. | No official request submitted - verbal request. | Walk up office next to Nate Giordano has Nate’s old pc hooked to it from when data was transferred to new pc. EWI to start in that office 10/4/10; | email to Mark Hazel 9/20 indicating the office has to be ready by 10/1/10. | Completed, profiles deleted, extra pc removed | Old pc picked up.
11 | Slusarczyk, Roxanne | 863008 |  | Class computer VELA not working | Submitted 9/2/10 | Incomplete. Can Roxy provide input? | Re-image or replace VELA Monday
12 | Slusarczyk, Roxanne |  |  | Structures Walk up area is unusable in Upper G Dock—not sure all pc’s have ever been set up but with all the computers sitting there it’s impossible to use |  | Incomplete | Repair or Replace walkup
13 | Slusarczyk, Roxanne | No official request submitted - verbal request. | No official request submitted - verbal request. | Unclass computer in my office area is not working | Email to Mark 9/20 | Incomplete | Repaor or Reimage Walkup
14 | Alampi, Nick | Need to look up | Need to look up | Supposed to have his computer replaced with a new PC. | Over 1 year | I’m pretty sure that my computer is in, but no one has acted on replacing it yet and I’m tired of bugging Mark Hazel about it (I contacted him at least twice about it). Looks like system needs to be imaged and delivered. Based on Track-IT, system is in and needs to be done
15 | Alampi, Nick | Need to look up | Need to look up | PC issues with 8 computers out on the floor . | 2010-09-08 | Originally when I put the request in, IT replied back to me saying that they do not have any flow down computers available and closed my WO request. Then I called up x7000 again and talked to Cliff and he said to just send him the list of PC’s (which I did in the email below) and he would look into seeing what needs to be done w/ the computers, whether it’s cleaning them up, upgrading their memory, etc…
16 | Kuipers, Vicki | 843661 |  | Replace old 21# CRT monitor for new 22# LCD monitor | 2010-08-09 | Monitor replaced.
17 | Kuipers, Vicki | No official request submitted - verbal request. | No official request submitted - verbal request. | When using headphones (for training, etc.), the sound still comes through the PC | 2010-07-14 | Nothing after 7/19 email reply | Deliver LCD display Monday
18 | Bill Trybulski | 835732 |  | Multiple log in dialog boxes when using the intranet (from the home page) | Late July | Still occurring - Have Call Center update
19 |  | 834735 |  |  |  | open new ticket july 7th. Has never worked for shireen | see Shireen - about this Monday;
[6 empty] | 12 minutes to login to use ms outlook | known ost file - corrupted - delet ost file.